## Drawing list
Rédigé par | A Diffuser au client | Prestations du contrat | Vendor doc ref | Vendor doc ID | Section | Number | Sheet | Last Revision | Format | Title | Issuer | AS BUILT | Pos | For information | For approval | Final | rev. 00 Transmittal n° | rev. 00 Issue date | rev. 00 Sent on | rev. 00 Expectative date of client comments | rev. 00 Comment received on | rev. 01 Transmittal n° | rev. 01 Issue date | rev. 01 Sent on2 | rev. 01 Expectative date of client comments | rev. 01 Comment received on
|  |  |  | 00 | LISTS | [5 empty] | ENG
DCC |  | x |  | RFQ | 00 | 001 | A | 00 | A3 | Project Documents list | ENG
[5 empty] | 00 | 001 | 100 | 00 |  | Document list - Gazeifier Section | GS
WO615 |  |  | G | 240 | 00 | 001 | 300 | 00 |  | Boiler document list
[5 empty] | 00 | 004 | A | 00 | A4 | Liste equipements - offre ENG | [6 empty] | offre | 2022-10-05
Proce | x | x |  |  | 00 | 2 | A | 00 | A4 | Equipment list | ENG
GS |  | x |  |  | 00 | 2 | 100 | 00 |  | Equipment list - Gazeifier Section GS | GS
OS |  | x |  |  | 00 | 2 | 200 | 00 |  | Equipment list - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 00 | 2 | 300 | 00 |  | Equipment list - Boiler Section BS | BS
ES |  | x |  |  | 00 | 2 | 400 | 00 |  | Equipment list - Electrical Generation Section ES | ES
TS |  | x |  |  | 00 | 2 | 500 | 00 |  | Equipment list - Gaz Treatment Section TS | TS
ENG |  | x |  |  | 00 | 2 | 600 | 00 |  | Equipment list - Utilities Section US | US
|  |  |  | 01 | FLOWSHEET | [5 empty] | ENG
PGO | x | x |  | RFQ | 01 | 001 | A | 5 | A4 | General Basis of Design | ENG |  |  |  | X |  | 1 | 2023-03-23 | 2023-03-23 |  | 2023-07-20
Proce |  |  |  |  | 01 | 1 | A | 00 | A1 | Process bloc diagram | ENG
| x | x |  |  | 01 | 002 | 001 | 1 | A1 | Schéma de procédé - GAZEIFICATION ET TRAITEMENT DES CENDRES | ENG |  |  |  | X |  | 5 | 2023-05-11 | 2023-05-12 |  | 2023-05-26 | 10 | 2023-06-13 | 2023-06-15 |  | 2023-07-20
[5 empty] | 01 | 002 | 101 | 1 | A1 | PFD Diagram-Case 01 | Licensor
[5 empty] | 01 | 002 | 102 | 1 | A1 | PFD Diagram-Case 02 | Licensor
[5 empty] | 01 | 002 | 103 | 1 | A1 | PFD Diagram-Case 03 | Licensor
[5 empty] | 01 | 002 | 100 | 1 | A1 | Schéma de procédé - GAZEIFICATION ET TRAITEMENT DES CENDRES | GS
| x | x |  | RFQ | 01 | 002 | 002 | 1 | A1 | Schéma de procédé - COMBUSTION ET PRODUCTION DE VAPEUR | ENG |  |  |  | X |  | 5 | 2023-05-11 | 2023-05-12 |  | 2023-07-19 | 17 | 2023-07-20 | 2023-07-20 |  | 2023-07-20
| x | x |  |  | 01 | 002 | 003 | 1 | A1 | Schéma de procédé - TRAITEMENT DES FUMEES ET PRODUCTION D'ELECTRICITE | ENG |  |  |  | X |  | 5 | 2023-05-11 | 2023-05-12 |  | 2023-05-26 | 10 | 2023-06-13 | 2023-06-15 |  | 2023-07-20
Proce | x | x |  |  | 01 | 004 | A | 00 | A4 | Operation manual | ENG
GS |  | x |  |  | 01 | 004 | 100 | 00 |  | Operation manual - Gazeifier Section GS | GS
OS |  | x |  |  | 01 | 004 | 200 | 00 |  | Operation manual - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | T | 900 | 01 | 004 | 300 | 00 |  | Operation manual - Boiler Section BS | BS
ES |  | x |  |  | 01 | 004 | 400 | 00 |  | Operation manual - Electrical Generation Section ES | ES
TS |  | x |  |  | 01 | 004 | 500 | 00 |  | Operation manual - Gaz Treatment Section TS | TS
MRO | x | x |  |  | 01 | 5 | A | 00 |  | Schema-interfaces | ENG |  |  | X |  |  | 8 | 2023-04-06 | 2023-05-30
Proce |  |  |  |  | 01 | 006 | A | 00 | A4 | Process description | ENG
GS |  |  |  |  | 01 | 006 | 100 | 00 |  | Process description - Gazeifier Section GS | GS
OS |  |  |  |  | 01 | 006 | 200 | 00 |  | Process description - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 01 | 006 | 300 | 00 |  | Process description - Boiler Section BS | BS
ES |  |  |  |  | 01 | 006 | 400 | 00 |  | Process description - Electrical Generation Section ES | ES
TS |  |  |  |  | 01 | 006 | 500 | 00 |  | Process description - Gaz Treatment Section TS | TS
Proce | x | x |  |  | 01 | 007 | A | 00 | A4 | Material and Utilities balances | ENG
GS |  | x |  |  | 01 | 007 | 100 | 00 |  | Material and Utilities balances - Gazeifier Section GS | GS
OS |  | x |  |  | 01 | 007 | 200 | 00 |  | Material and Utilities balances - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 01 | 007 | 300 | 00 |  | Material and Utilities balances - Boiler Section BS | BS
ES |  | x |  |  | 01 | 007 | 400 | 00 |  | Material and Utilities balances - Electrical Generation Section ES | ES
TS |  | x |  |  | 01 | 007 | 500 | 00 |  | Material and Utilities balances - Gaz Treatment Section TS | TS
|  | x |  |  | 01 | 8 | A | 00 |  | Bilan des utilités
[5 empty] | 01 | 8 | 100 | 00 |  | UtilitiesS & Consumer List - Gazeifier Section GS
WO615 |  |  | P | 153 | 01 | 8 | 300 | 00 |  | UTILITIES LIST (with consumptions)
|  | x |  |  | 01 | 9 | A | 00 |  | Liste des émissions / rejets
[5 empty] | 01 | 9 | 100 | 00 |  | Process description - Gazeifier Section GS
WO615 |  |  | hold | hold | 01 | 9 | 300 | 00 |  | Liste des émissions / rejets
|  | x |  |  | 01 | 10 | A | 00 |  | MSD et Material selection (report)
[5 empty] | 01 | 10 | 100 | 00 |  | MSD et Material selection - Gazeifier Section GS
WO615 |  |  | hold | hold | 01 | 10 | 300 | 00 |  | MSD et Material selection (report)
[5 empty] | 01 | 11 | 400 | 00 |  | Steam quality
|  |  |  | 02 | P.I.D (PIPING AND INSTRUMENTATION DIAGRAMS) | [5 empty] | ENG
Proce | x | x |  | RFQ | 02 | 1 | 001 | 1 | A1 | Process and Instrument Diagram - Instructions, Symbols, Standards | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
Proce | x | x |  |  | 02 | 100 | 001 | 1 | A1 | Process and Instrument Diagram - Gazeifier Section Interfaces | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
GS | x | x |  |  | 02 | 1 | 101 | 00 | A1 | Process and Instrument Diagram - xx | GS
GS | x | x |  |  | 02 | 1 | 102 | 00 | A1 | Process and Instrument Diagram - xx | GS
Proce | x | x |  |  | 02 | 200 | 001 | 1 | A1 | Process and Instrument Diagram - Combustion | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
OS | x | x |  |  | 02 | 201 | 001 | 1 | A1 | Process and Instrument Diagram - Oxydation | OS |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
OS | x | x |  |  | 02 | 1 | 201 | 00 | A1 | Process and Instrument Diagram - xx | OS
Proce | x | x |  |  | 02 | 300 | 001 | 1 | A1 | Process and Instrument Diagram - chaudière & Degazeur | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
WO615 | x | x | P | 100 | 02 | 1 | 301 | 00 | A1 | Process and Instrument Diagram - STEAM AND WATER SYSTEM | BS
WO615 | x | x | P | 101 | 02 | 1 | 302 | 00 | A1 | Process and Instrument Diagram - BOILER FEEDWATER SYSTEM | BS
WO615 |  |  | P | 109 | 02 | 1 | 303 | 00 | A1 | Process and Instrument Diagram - CHEMICAL INJECTION SYSTEM | BS
WO615 |  |  | P | 113 | 02 | 1 | 304 | 00 | A1 | Process and Instrument Diagram - SOOTBLOWER SYSTEM | BS
Proce | x | x |  |  | 02 | 400 | 001 | 1 | A1 | Process and Instrument Diagram - Electrical Generation Section Interfaces | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
ES | x | x |  |  | 02 | 1 | 401 | 00 | A1 | Process and Instrument Diagram - xx | ES
ES | x | x |  |  | 02 | 1 | 402 | 00 | A1 | Process and Instrument Diagram - xx | ES
Proce | x | x |  |  | 02 | 500 | 001 | 1 | A1 | Process and Instrument Diagram - Tratement des fumées | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
TS | x | x |  |  | 02 | 501 | 001 | 1 | A1 | Process and Instrument Diagram - Traitement des cendres | TS |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
TS | x | x |  |  | 02 | 1 | 502 | 00 | A1 | Process and Instrument Diagram - xx | TS
[5 empty] | 02 | 600 | 001 | 1 | A1 | Process and Instrument Diagram - Utilités Gazeuses |  |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
Proce | x | x |  |  | 02 | 601 | 001 | 1 | A1 | Process and Instrument Diagram - Cooling water system/Utilités liquides | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09
Proce | x | x |  |  | 02 | 602 | 001 | 1 | A1 | Process and Instrument Diagram - Boiler feed water system/Vapeur et condensats | ENG |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
[5 empty] | 02 | 603 | 001 | 1 | A1 | Process and Instrument Diagram - Eau de refroidissement |  |  |  |  | X |  | 21 | 2023-07-24 | 2023-07-25 |  | 2023-07-31 | 27 | 2023-10-25 | 2023-10-25 | 2023-11-09 | 2023-11-02
Proce | x | x |  |  | 02 | 1 | +603 | 00 | A1 | Process and Instrument Diagram - Drainage System | ENG
Proce | x | x |  |  | 02 | 1 | 604 | 00 | A1 | Process and Instrument Diagram - Gas utility networks | ENG
Proce | x | x |  |  | 02 | 1 | 605 | 00 | A1 | Process and Instrument Diagram - Liquid Utility networks | ENG
Proce | x | x |  |  | 02 | 1 | 606 | 00 | A1 | Process and Instrument Diagram - Steam & Condensates networks | ENG
|  |  |  | 03 | Plan Masse | [5 empty] | ENG
BE |  | x |  |  | 03 | 001 | 001 | 00 | A1 | Location plan | ENG
|  |  |  | 04 | PLOT PLAN | [5 empty] | ENG
BE | x | x |  | RFQ | 04 | 001 | 001 | 2 | A1 | Plot Plan General | ENG |  |  |  | X |  | 6 | 2023-05-22 | 2023-05-22 |  | 2023-05-26 |  | 2023-11-17
[5 empty] | 04 | 001 | 100 | 00 | A1 | Plot Plan - Gazeifier Section
[5 empty] | 04 | 001 | 200 | 00 | A1
WO615 |  |  | M | 010 | 04 | 001 | 300 | 00 | A1 | BOILER GENERAL LAYOUT
[5 empty] | 04 | 001 | 400 | 00 | A1
|  | x |  |  | 04 | 001 | 002 | 1 | A1 | Plan d'implantation - Batiment d'exploitation |  |  |  | X |  |  | 15 | 2023-06-30 | 2023-06-30 |  |  | 030 | 2023-12-11 | 2023-12-12
BE |  | x |  |  | 04 | 003 | A | 00 | A3 | Battery limits - with existing PLANT (ISBL) | ENG
GS |  |  |  |  | 04 | 003 | 100 | 00 | A3 | Battery limits for Gazeifier Section | GS
OS |  |  |  |  | 04 | 003 | 200 | 00 | A3 | Battery limits for Oxidizer and ashes Furnace Section | OS
BS |  |  |  |  | 04 | 003 | 300 | 00 | A3 | Battery limits for Boiler Section | BS
ES |  |  |  |  | 04 | 003 | 400 | 00 | A3 | Battery limits for Electrical Generation Section | ES
TS |  |  |  |  | 04 | 003 | 500 | 00 | A3 | Battery limits for Gaz Treatment Section | TS
BE |  |  |  |  | 04 | 005 | 001 | 00 | A1 | Utility stations locations | ENG
|  |  |  | 05 | ORGANIZATION- PROCEDURE AND CONTRACTUAL DRAWING | [5 empty] | ENG
PGO | x | x |  |  | 05 | 001 | A | 00 | A4 | Coordination Procedure | ENG |  |  | X |  |  | 2 | 2023-03-23 | 2023-03-27
PGO | x | x |  |  | 05 | 002 | A | 00 | A4 | Project Execution Plan | ENG | [5 empty] | 23 | 2023-06-02 | 2023-08-25 |  |  | 32 | 2023-12-19 | 2023-12-19
DCC | x | x |  | RFQ | 05 | 003 | A | 00 | A4 | Procedure for numbering documents and computer files | ENG |  |  | X |  |  | 4 | 2023-03-24 | 2023-05-10
PGO |  |  |  |  | 05 | 004 | A | 00 | A4 | Project Procurement Plan | ENG
DCC |  |  |  | RFQ | 05 | 005 | A | 00 | A4 | Vendor Documentation Procedure | ENG
DCC | x | x |  | RFQ | 05 | 006 | A | 00 | A4 | Spare parts procedure | ENG |  |  | X |  |  | 4 | 2023-03-24 | 2023-05-10
DCC |  |  |  | RFQ | 05 | 007 | A | 00 | A4 | Instructions for packing / marking / shipping | ENG
| x | x |  |  | 05 | 008 | A | 00 | A4 | Progress Procedure
[5 empty] | 05 | 009 | A | 00 | A4 | Procurement procedure for site activities
site |  |  |  |  | 05 | 010 | A | 00 | A4 | NUMBERING PROCEDURE | ENG
| x | x |  |  | 05 | 11 | A | 00 | A4 | Interface procedure | ENG
|  |  |  | 06 | QUALITY – INSPECTION | [5 empty] | ENG
PGO |  |  |  |  | 06 | 001 | A | 00 | A4 | Plan Qualite Projet | ENG
PGO | x | x |  | RFQ | 06 | 002 | A | 00 | A4 | Inspection QA / QC vendors procedure | ENG |  |  | X |  |  | 4 | 2023-03-24 | 2023-05-10
PGO | x | x |  | RFQ | 06 | 003 | A | 00 | A4 | Coordination procedure for Inspection | ENG |  |  | X |  |  | 4 | 2023-03-24 | 2023-05-10
INS |  |  |  | ? | 06 | 005 | A | 00 | A4 | Partial and complete loop test Procedure | ENG
PGO |  |  |  |  | 06 | 006 | A | 00 | A4 | Site Activities procedure - Quality and controls | ENG
PGO |  |  |  |  | 06 | 007 | A | 00 | A4 | Inspection procedures for piping - Workshop and site | ENG
PGO |  |  |  |  | 06 | 10 | A | 0 | A4 | Inpection and Test Plan | ENG
GS |  |  |  |  | 06 | 10 | 100 | 0 | A4 | Inpection and Test Plan - Gazeifier Section GS | GS
OS |  |  |  |  | 06 | 10 | 200 | 0 | A4 | Inpection and Test Plan - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | Q | 900 | 06 | 10 | 300 | 0 | A4 | Inpection and Test Plan - Boiler Section BS | BS
ES |  |  |  |  | 06 | 10 | 400 | 0 | A4 | Inpection and Test Plan - Electrical Generation Section ES | ES
TS |  |  |  |  | 06 | 10 | 500 | 0 | A4 | Inpection and Test Plan - Gaz Treatment Section TS | TS
| x | x |  |  | 06 | 10 |  | 0 | A4 | Deviation list
[5 empty] | 06 | 10 | 100 | 0 | A4 | Deviation list | GS
WO615 |  |  | hold | hold | 06 | 10 | 300 | 0 | A4 | Deviation list
|  |  |  | 07 | SCHEDULE | [5 empty] | ENG
PLN | x | x |  |  | 07 | 001 | A | 00 | A4 | Project overall schedule - Level 2 | ENG
[5 empty] | 07 | 001 | 100 | 00 | A4 | Project overall schedule - Level 2 - Gazeifier Section GS | GS
[5 empty] | 07 | 001 | 200 | 00 | A4 | Project overall schedule - Level 2 - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | G | 001 | 07 | 001 | 300 | 00 | A4 | Project overall schedule - Level 2 - Boiler Section BS | BS
[5 empty] | 07 | 001 | 400 | 00 | A4 | Project overall schedule - Level 2 - Electrical Generation Section ES | ES
[5 empty] | 07 | 001 | 500 | 00 | A4 | Project overall schedule - Level 2 - Gaz Treatment Section TS | TS
PLN | x |  |  |  | 07 | 003 | A | 00 | A4 | Construction schedule - Level 3 | ENG
[5 empty] | 07 | 003 | 100 | 00 | A4 | Construction schedule - Level 3 - Gazeifier Section GS | GS
[5 empty] | 07 | 003 | 200 | 00 | A4 | Construction schedule - Level 3 - Oxidizer and ashes Furnace Section OS | OS
[5 empty] | 07 | 003 | 300 | 00 | A4 | Construction schedule - Level 3 - Boiler Section BS | BS
[5 empty] | 07 | 003 | 400 | 00 | A4 | Construction schedule - Level 3 - Electrical Generation Section ES | ES
[5 empty] | 07 | 003 | 500 | 00 | A4 | Construction schedule - Level 3 - Gaz Treatment Section TS | TS
|  |  |  | 08 | PROCESS | [5 empty] | ENG
Proce | x | x |  |  | 08 | 001 | A | 00 | A4 | Process Basis of Design | ENG
Proce |  |  |  |  | 08 | 2 | A | 00 | A4 | Process Data Sheet | ENG
Proce |  |  |  |  | 08 | 2 | 100 | 00 | A4 | Process Data Sheet - Gazeifier Section GS | Licensor
23526 |  |  | 23526-232-103 |  | 08 | 2 | 101 | 00 | A4 | DS Gasifier (G-101) | Licensor
23526 |  |  | 23527-232-104 |  | 08 | 2 | 102 | 00 | A4 | DS Blower | Licensor
23526 |  |  | 23526-232-105 |  | 08 | 2 | 103 | 00 | A4 | DS Start up burner | Licensor
23526 |  |  | 23526-232-106 |  | 08 | 2 | 104 | 00 | A4 | DS Rotary valve | Licensor
23526 |  |  | 23526-232-107 |  | 08 | 2 | 105 | 00 | A4 | DS Feeder Screw (C-102 A_B) | Licensor
23526 |  |  | 23526-232-108 |  | 08 | 2 | 106 | 00 | A4 | DS Gasifier Bottom Extraction (C-103) | Licensor
23526 |  |  | 23526-232-109 |  | 08 | 2 | 107 | 00 | A4 | DS Screener (S-103) | Licensor
23526 |  |  | 23526-232-110 |  | 08 | 2 | 108 | 00 | A4 | DS Fluidization air blower | Licensor
23526 |  |  | 23526-232-111 |  | 08 | 2 | 109 | 00 | A4 | DS Syngas Cyclone (S-101) | Licensor
23526 |  |  | 23526-232-112 |  | 08 | 2 | 110 | 00 | A4 | DS APT Cyclone | Licensor
23526 |  |  | 23526-232-113 |  | 08 | 2 | 111 | 00 | A4 | DS Bucket Elevator (C-107) | Licensor
23526 |  |  | 23526-232-114 |  | 08 | 2 | 112 | 00 | A4 | DS Bed Extraction (C-104) | Licensor
23526 |  |  | 23526-232-115 |  | 08 | 2 | 113 | 00 | A4 | DS Bed Feeding (C-106) | Licensor
23526 |  |  | 23526-232-116 |  | 08 | 2 | 114 | 00 | A4 | DS Fresh Bed Screw (C-105) | Licensor
23526 |  |  | 23526-232-117 |  | 08 | 2 | 115 | 00 | A4 | DS Bottom Ash Feeding Screw (C-1xx) | Licensor
23526 |  |  | 23526-232-118 |  | 08 | 2 | 116 | 00 | A4 | DS Flying Ash Cooler (C-1xx) | Licensor
23526 |  |  | 23526-232-119 |  | 08 | 2 | 117 | 00 | A4 | DS MBM Feeder (C-1xx A_B) | Licensor
23526 |  |  | 23526-232-120 |  | 08 | 2 | 201 | 00 | A4 | DS Syngas Burner (X-201) | Licensor
23526 |  |  | 23526-232-121 |  | 08 | 2 | 202 | 00 | A4 | DS Combustion Air Fan (B-201) | Licensor
Proce |  |  |  |  | 08 | 2 | 200 | 00 | A4 | Process Data Sheet - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | P | 501 | 08 | 2 | 300 | 00 | A4 | Process Data Sheet - Boiler Section BS | BS
Proce |  |  |  |  | 08 | 2 | 400 | 00 | A4 | Process Data Sheet - Electrical Generation Section ES | ES
Proce |  |  |  |  | 08 | 2 | 500 | 00 | A4 | Process Data Sheet - Gaz Treatment Section TS | TS
Proce |  |  |  |  | 08 | 2 | A | 00 | A4 | Process Data Sheet - Utilities Section US | ENG
Proce | x | x |  |  | 08 | 003 | A | 00 | A4 | Cause and Effect Matrix | ENG
GS |  |  |  |  | 08 | 003 | 100 | 00 | A3 | Cause and Effect Matrix - Gazeifier Section GS | GS
OS |  |  |  |  | 08 | 003 | 200 | 00 | A3 | Cause and Effect Matrix - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | S | 152 | 08 | 003 | 300 | 00 | A3 | Cause and Effect Matrix - Boiler Section BS | BS
ES |  |  |  |  | 08 | 003 | 400 | 00 | A3 | Cause and Effect Matrix - Electrical Generation Section ES | ES
TS |  |  |  |  | 08 | 003 | 500 | 00 | A3 | Cause and Effect Matrix - Gaz Treatment Section TS | TS
Proce |  | x |  |  | 08 | 004 | A | 00 | A3 | Logic diagram for Security & Automation | ENG
GS |  |  |  |  | 08 | 004 | 100 | 00 | A3 | Logic diagram - Gazeifier Section GS | GS
OS |  |  |  |  | 08 | 004 | 200 | 00 | A3 | Logic diagram - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | S | 330 | 08 | 004 | 300 | 00 | A3 | Logic diagram - Boiler Section BS | BS
ES |  |  |  |  | 08 | 004 | 400 | 00 | A3 | Logic diagram - Electrical Generation Section ES | ES
TS |  |  |  |  | 08 | 004 | 500 | 00 | A3 | Logic diagram - Gaz Treatment Section TS | TS
ENG
|  |  |  | 09 | TESTS | [5 empty] | ENG
PGO | x | x |  |  | 09 | 001 | A | 00 | A4 | Acceptance Test Procedure | ENG
ES |  | x |  |  | 09 | 001 | 100 | 00 | A3 | #REF! | GS
ES |  | x |  |  | 09 | 001 | 200 | 00 | A3 | #REF! | OS
WO615 |  | x | hold | hold | 09 | 001 | 300 | 00 | A3 | #REF! | BS
ES |  | x |  |  | 09 | 001 | 400 | 00 | A3 | #REF! | ES
ES |  | x |  |  | 09 | 001 | 500 | 00 | A3 | #REF! | TS
[5 empty] | 09 | 10 | 100 | 00 | A3 | PERFORMANCE TEST PROCEDURE
WO615 |  |  | P | 900 | 09 | 10 | 300 | 00 | A3 | PERFORMANCE TEST PROCEDURE
|  |  |  | 13 | Ballon
WO615 |  |  | M | 809 | 13 | 002 | 301 | 0 |  | DEAERATOR GENERAL ASSEMBLY DRAWING
|  |  |  | 17 | Production de Gaz | [5 empty] | ENG
[5 empty] | 17 | 2 | A | 0 |  | Duty Specification Gazeification | ENG
[5 empty] | 17 | 1 | A | 0 | A4 | Gasifier calculation note | Licensor
|  |  |  | 21 | Chaudieres | [5 empty] | ENG
[5 empty] | 21 | 301 | A | 0 | A4 | PDS_WHB_2023 3003
WO615 |  |  | M | 137 | 21 | 1 | 301 | 0 | A1 | DOWNCOMERS PIPING GENERAL ASSEMBLY DRAWING
WO615 |  |  | M | 138 | 21 | 1 | 302 | 0 | A1 | RISERS PIPING GENERAL ASSEMBLY DRAWING
WO615 |  |  | M | 514 | 21 | 1 | 303 | 0 | A1 | SKIN CASING ASSEMBLY DRAWING
WO615 |  |  | M | 542 | 21 | 1 | 304 | 0 | A1 | STEAM DRUM INTERNAL ASSEMBLY
WO615 |  |  | M | 590 | 21 | 1 | 305 | 0 | A1 | BUCKSTAYS ASSEMBLY AND DETAIL DRAWING
WO615 |  |  | M | 834 | 21 | 1 | 306 | 0 | A1 | SOOTBLOWERS GENERAL ASSEMBLY
WO615 |  |  | P | 518 | 21 | 1 | 307 | 0 | A1 | SOOTBLOWER DATA SHEET AND WIRING DIAGRAM
WO615 |  |  | M | 521 | 21 | 1 | 310 | 0 | A1 | SKIN CASING HOPPER
WO615 |  |  | M | 522 | 21 | 1 | 311 | 0 | A1 | SKIN CASING HOPPER
|  |  |  | 22 | Oxydizer | [5 empty] | ENG
[5 empty] | 22 | 200 | A | 0 | A4 | Requisition for Oxidiser | ENG
[5 empty] | 22 | 201 | A | 0 | A4 | Duty spec Oxidizer | ENG
[5 empty] | 22 | 200 | 001 | 0 | A1 | Equipment Sketch Oxidizer | ENG
|  |  |  | 23 | Exchangers
WO615 |  |  | P | 508 | 23 | 1 | 301 | 0 | A4 | HEAT EXCHANGE DATA SHEET
WO615 |  |  | hold | hold | 23 | 2 | 301 | 0 | A1 | HEAT EXCHANGEr general Arrangement Drawing
[5 empty] | 23 | 2 | 101 | 0 | A4 | HEAT EXCHANGE DATA SHEET | Licensor
|  |  |  | 26 | BURNERS | [5 empty] | ENG
[5 empty] | 26 | 301 | 200 | 00 | A4 | Calculation sheet - Oxidizer Burner | OS
OS |  |  |  |  | 26 | 311 | 200 | 00 | A1 | General Arrangement drawing - Oxidizer Burner | Licensor
OS |  |  |  |  | 26 | 312 | 200 | 00 | A1 | Detail Drawing - Oxidizer Burner | Licensor
|  |  |  | 27 | NA | [5 empty] | ENG
ENG
ENG
ENG
|  |  |  | 28 | STACK | [5 empty] | ENG
TS |  | x |  |  | 28 | 001 | 500 | 00 | A4 | Process Data Sheet - Vent Stack | TS
TS |  |  |  |  | 28 | 10 | 500 | 00 | A4 | Calculation Sheet - Vent Stack | TS
TS |  |  |  |  | 28 | 20 | 500 | 00 | A1 | General Arrangement drawings - Vent Stack | TS
TS |  |  |  |  | 28 | 30 | 500 | 00 | A1 | Detail Drawing - Vent Stack - | TS
TS |  |  |  |  | 28 | 31 | 500 | 00 | A1 | DETAIL DRAWING - ANCHOR - STACK | TS
TS |  |  |  |  | 28 | 32 | 500 | 00 | A1 | DETAIL DRAWING - FOUNDATION - STACK | TS
TS |  |  |  |  | 28 | 33 | 500 | 00 | A1 | General Arrangement drawings - Stack Structure | TS
TS |  |  |  |  | 28 | 34 | 500 | 00 | A1 | Detail Drawing - Stack Structure | TS
|  |  |  | 29 | REFRACTORIES | [5 empty] | ENG
[5 empty] | 29 | 1 | 100 | 00 | A3 | Refractory Gazeifier Section | GS
OS |  |  |  |  | 29 | 1 | 200 | 00 | A3 | Mechanical Data Sheet - Refractory Oxidizer Section | OS
OS |  | x |  |  | 29 | 10 | 200 | 00 | A4 | Requisition - Refractory works ( Oxidizer Section) | OS
OS |  |  |  |  | 29 | 20 | 200 | 00 | A4 | Calculation Sheet - Refractory Oxidizer Section | OS
OS |  |  |  |  | 29 | 30 | 200 | 00 | A1 | General Arrangement drawings - Refractory Oxidizer Section | OS
OS |  |  |  |  | 29 | 31 | 200 | 00 | A1 | Detail Drawing - Refractory Oxidizer Section | OS
OS |  |  |  |  | 29 | 21 | 200 | 00 | A4 | Thermal calculations | OS
OS |  |  |  |  | 29 | 40 | 200 | 00 | A1 | Oxydizer - Main cylinder - Refractory lining | OS
OS |  |  |  |  | 29 | 41 | 200 | 00 | A1 | Oxydizer - Main cylinder - Anchors layout | OS
OS |  |  |  |  | 29 | 42 | 200 | 00 | A1 | Oxydizer - Connection to WHB - Refractory lining | OS
OS |  |  |  |  | 29 | 43 | 200 | 00 | A1 | Oxydizer - Connection to WHB - Anchors layout | OS
WO615 |  |  | hold | hold | 29 | 31 | 300 | 00 | A1 | Detail Drawing - Refractory areas
|  |  |  | 30 | BLOWERS | [5 empty] | ENG
OS |  | x |  |  | 30 | 001 | 200 | 00 | A4 | Process Data Sheet - Air Blower | OS
OS |  |  |  |  | 30 | 10 | 200 | 00 | A4 | Requisition - Air Blower | OS
OS |  |  |  |  | 30 | 20 | 200 | 02 | A4 | Calculation sheet - Air Blowers | OS
OS |  |  |  |  | 30 | 30 | 200 | 01 | A3 | General Arrangement drawing - Air Blowers | OS
OS |  |  |  |  | 30 | 40 | 200 | 00 |  | Motor data sheet data sheet and drawing - Air Blowers - | OS
|  |  |  | 31 | COMPRESSOR | [5 empty] | ENG
|  |  |  | 32 | PUMPS | [5 empty] | ENG
WO615 |  |  | hold | hold | 32 | 1 | 301 | 0 | A4 | FEEDWATER PUMP Data sheet
WO615 |  |  | M | 820 | 32 | 2 | 301 | 0 | A4 | FEEDWATER PUMP AND MOTOR GENERAL ASSEMBLY
|  |  |  | 33 | Autres machines / Turbine Vapeur
[5 empty] | 30 | 001 | 400 | 00 | A4 | Process Data Sheet - Steam Turbine
|  |  |  | 34 | Conveyors | [5 empty] | ENG
[5 empty] | 34 | 1 | 001 | 0 | A1 | Plan Guide Implantation Vis sans fin
OS |  |  |  |  | 34 | 001 | 200 | 00 | A4 | Process Data Sheet - Screw conveyors | OS
[5 empty] | 34 | 10 | 100 | 00 | A4 | Process Data Sheet - Magnetic Screw conveyors - Gazeifier Section GS | GS
[5 empty] | 34 | 001 | 200 | A | A4 | Requisition for Ashes Handling System
[5 empty] | 34 | 001 | 300 | 00 | A4 | Process Data Sheet - Screw conveyors - Boiler Section BS
[5 empty] | 34 | 001 | 400 | 00 | A4 | Process Data Sheet - Screw conveyors - Electrical Generation Section ES
[5 empty] | 34 | 2 | 200 | 00 | A4 | General Arrangement drawing - Screw conveyors
[5 empty] | 34 | 2 | 100 | 00 | A3 | General Arrangement drawing - Screw conveyors - Gazeifier Section GS | GS
[5 empty] | 34 | 2 | 200 | A | A4 | Specification for Ashes Handling System
[5 empty] | 34 | 2 | 300 | 00 | A3 | General Arrangement drawing - Screw conveyors - Boiler Section BS
[5 empty] | 34 | 2 | 400 | 00 | A3 | General Arrangement drawing - Screw conveyors - Electrical Generation Section ES
[5 empty] | 34 | 3 | 200 | 00 | A4 | Motor data sheet data sheet and drawing - Screw conveyors -
[5 empty] | 34 | 3 | 100 | 00 | A4 | Motor data sheet data sheet and drawing - Screw conveyors - Gazeifier Section GS | GS
[5 empty] | 34 | 3 | 200 | 00 | A4 | Motor data sheet data sheet and drawing - Screw conveyors - Oxidizer and ashes Furnace Section OS
[5 empty] | 34 | 3 | 300 | 00 | A4 | Motor data sheet data sheet and drawing - Screw conveyors - Boiler Section BS
[5 empty] | 34 | 3 | 400 | 00 | A4 | Motor data sheet data sheet and drawing - Screw conveyors - Electrical Generation Section ES
[5 empty] | 34 | 4 | 200 | 0 | A1 | Plan Guide Implantation Vis sans fin
[5 empty] | 34 | 4 | 200 | 00 | A3 | Detail drawings
OS |  |  |  |  | 34 | 4 | 100 | 00 | A3 | Detail drawings - Gazeifier Section GS | GS
OS |  |  |  |  | 34 | 4 | 200 | 00 | A3 | Detail drawings - Oxidizer and ashes Furnace Section OS | OS
OS |  |  |  |  | 34 | 4 | 301 | 00 | A3 | Detail drawings - Boiler Section BS | OS
[5 empty] | 34 | 4 | 400 | 00 | A3 | Detail drawings - Electrical Generation Section ES | OS
[5 empty] | 34 | 5 | 200 | A | A4 | Specification for Ashes Handling System List
|  |  |  | 35 | CLIMATISATION GROUPES FROID
[5 empty] | 40 | 1 | 100 | 00 | A3 | Conveyor screw cooling system - PID | GS
[5 empty] | 40 | 2 | 100 | 00 | 00 | Conveyor screw cooling system - calculation note | GS
[5 empty] | 40 | 3 | 100 | 00 | 00 | Conveyor screw cooling system - Arrangement drawing | GS
|  |  |  | 40 | Batiment béton
|  | x |  |  | 40 | 1 |  |  |  | Plan guide bâtiment
| x |  |  |  | 40 | 1 | 600 | 00 | A3 | Schémas de principe du poste de commande ISBL
|  |  |  | 41 | CANIVEAUX & CIRCUITS ENTERRES
|  | x |  |  | 41 | 1 | 001 | 00 | A1 | Plans d'interfaces avec les réseaux enterrés | [6 empty] | 030 | 2023-12-11 | 2023-12-12
| x |  |  |  | 41 | 1 | 100 | 00 | A3 | Plans d'interfaces réseaux enterrés et batiment
[5 empty] | 41 | 1 | 300 | 00 | A3 | Plans d'interfaces réseaux enterrés et batiment
| x |  |  |  | 41 | 1 | 200 | 00 | A3 | Plans d'interfaces réseaux enterrés et batiment
| x |  |  |  | 41 | 1 | 400 | 00 | A3 | Plans d'interfaces réseaux enterrés et batiment
|  |  |  | 43 | PLAN D’AIRE ET DESCENTES DE CHARGES | [5 empty] | ENG
[5 empty] | 43 | 1 | 001 | 0 | A1 | Plan Guide - INTERFACES - COUPES DES NIVEAUX DE POSE DES EQUIPEMENTS | ENG | [10 empty] | 030 | 2023-12-06 | 2023-12-12
[5 empty] | 43 | 2 | 001 | 0 | A1 | Plan Descentes de charges | ENG | [6 empty] | 2023-05-01 |  |  |  | 030 | 2023-12-12 | 2023-12-12
[5 empty] | 43 | 3 | 001 | 0 |  | Interfaces Génie Civil (Fichier 3D ifc) | ENG | [5 empty] | 33 | 2023-12-19 | 2023-12-20
|  |  |  | 45 | BATIMENT, STRUCTURE METALLIQUE PRINCIPALE, ESTACADE
[5 empty] | 45 | 1 | 100 | 00 | A1 | FOUNDATION PLAN ASSEMBLY WITH LOADS | GS
WO615 |  |  | M | 020 | 45 | 1 | 300 | 00 | A1 | FOUNDATION PLAN ASSEMBLY WITH LOADS
STR |  | x |  |  | 45 | 1 | 500 | 00 | A4 | Structural basis of design | ENG
STR |  | x |  |  | 45 | 2 | A | 00 | A4 | Steel structure GAD | ENG
STR |  | x |  |  | 45 | 3 | A | 00 | A4 | Calculation note - Steel Structure Works | ENG
GS |  |  |  |  | 45 | 3 | 100 | 00 | A4 | Calculation note - Steel Structure Works - Gazeifier Section GS | GS
OS |  |  |  |  | 45 | 3 | 200 | 00 | A4 | Calculation note - Steel Structure Works - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | P | 010 | 45 | 3 | 300 | 00 | A4 | Calculation note - Steel Structure Works - Boiler Section BS | BS
ES |  |  |  |  | 45 | 3 | 400 | 00 | A4 | Calculation note - Steel Structure Works - Electrical Generation Section ES | ES
TS |  |  |  |  | 45 | 3 | 500 | 00 | A4 | Calculation note - Steel Structure Works - Gaz Treatment Section TS | TS
US |  |  |  |  | 45 | 3 | 600 | 00 | A4 | Calculation note - Steel Structure Works - Utilities Section US | US
[5 empty] | 45 | 5 | 100 | 00 | A4 | FOUNDATION ANCHORING DETAILS | GS
WO615 |  |  | P | 025 | 45 | 5 | 300 | 00 | A4 | FOUNDATION ANCHORING DETAILS | BS
STR |  | x |  |  | 45 | 10 | 001 | 00 |  | DWG - STEEL STRUCTURE | ENG
GS |  |  |  |  | 45 | 10 | 100 | 00 |  | DWG - STEEL STRUCTURE - Gazeifier Section GS | Licensor
[5 empty] | 45 | 10 | 101 | 00 | A1 | Structure Drawing Plant N nnn | Licensor
[5 empty] | 45 | 10 | 102 | 00 | A1 | Structure Drawing Plant N nnn | Licensor
[5 empty] | 45 | 10 | 103 | 00 | A1 | Structure Drawing Plant N nnn | Licensor
[5 empty] | 45 | 10 | 104 | 00 | A1 | Structure Elevation A | Licensor
[5 empty] | 45 | 10 | 105 | 00 | A1 | Structure Elevation b | Licensor
[5 empty] | 45 | 10 | 106 | 00 | A1 | Structure Elevation c | Licensor
[5 empty] | 45 | 10 | 107 | 00 | A1 | Structure Elevation d | Licensor
OS |  |  |  |  | 45 | 10 | 200 | 00 |  | DWG - STEEL STRUCTURE - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | M | 700 | 45 | 10 | 300 | 00 |  | DWG - STEEL STRUCTURE - Boiler Section BS | BS
ES |  |  |  |  | 45 | 10 | 400 | 00 |  | DWG - STEEL STRUCTURE - Electrical Generation Section ES | ES
TS |  |  |  |  | 45 | 10 | 500 | 00 |  | DWG - STEEL STRUCTURE - Gaz Treatment Section TS | TS
US |  |  |  |  | 45 | 10 | 600 | 00 |  | DWG - STEEL STRUCTURE - Utilities Section US | US
[5 empty] | 45 | 12 | 103 | 00 |  | DWG - STEEL STRUCTURE - pltf & access ways - Gazeifier Section GS | GS
|  |  |  | 46 | OTHERS STRUCTURES AND PIPING SUPPORT | [5 empty] | ENG
BE |  |  |  |  | 46 | 001 | 001 | 00 | A1 | DWG - Structural Pipe Support Locations | ENG
GS |  |  |  |  | 46 | 001 | 100 | 00 | A1 | DWG - Structural Pipe Support Locations - Gazeifier Section GS | GS
OS |  |  |  |  | 46 | 001 | 200 | 00 | A1 | DWG - Structural Pipe Support Locations - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | M | 330 | 46 | 001 | 300 | 00 | A1 | DWG - Structural Pipe Support Locations - Boiler Section BS | BS
ES |  |  |  |  | 46 | 001 | 400 | 00 | A1 | DWG - Structural Pipe Support Locations - Electrical Generation Section ES | ES
TS |  |  |  |  | 46 | 001 | 500 | 00 | A1 | DWG - Structural Pipe Support Locations - Gaz Treatment Section TS | TS
US |  |  |  |  | 46 | 001 | 600 | 00 | A1 | DWG - Structural Pipe Support Locations - Utilities Section US | US
|  |  |  | 47 | RACKS | [5 empty] | ENG
STR |  |  |  |  | 47 | 001 | 001 | 00 | A1 | Guide drawing - Pipe rack layout plan | ENG
STR |  |  |  |  | 47 | 2 | A | 00 | A4 | Calculation Notes | ENG
STR |  |  |  |  | 47 | 10 | 001 | 00 | A1 | Guide drawing - Steel Structure Pipe Rack details | ENG
|  |  |  | 50 | MANIFOLDS ON BATTERY LIMIT | [5 empty] | ENG
Proce |  | x |  |  | 50 | 001 | A | 1 | A3 | Piping Lines List | ENG | [5 empty] | offre | 2022-02-03 |  |  |  | VEN | 2023-07-25
[5 empty] | 50 | 001 | 100 | 1 | A3 | Piping Lines List
WO615 |  |  | P | 150 | 50 | 001 | 300 | 1 | A3 | Piping Lines List
Proce | x | x |  |  | 50 | 002 | A | 1 | A4 | Piping Class | ENG |  |  | X |  |  | 11 | 2023-06-15 | 2023-06-15 |  |  | 29 | 2023-11-24 | 2023-12-07
WO615 |  |  | P | 170 | 50 | 002 | 300 | 1 | A4 | PIPING CLASSES Section 300 | [11 empty] | 29 | 2023-11-24 | 2023-12-07
BE |  | x |  |  | 50 | 003 | A | 00 | A4 | Calculated Line List | ENG
[5 empty] | 50 | 003 | 100 | 00 | A4 | Calculation note | GS
BE |  | x |  |  | 50 | 004 | A | 00 | A4 | Tie-in List | ENG
BE |  |  |  |  | 50 | 005 | A | 00 | A4 | Special Valves List | ENG
[5 empty] | 50 | 005 | 100 | 00 | A4 | Valves List
WO615 |  |  | P | 151 | 50 | 005 | 300 | 00 | A4 | Valves List
BE |  |  |  |  | 50 | 006 | A | 00 | A4 | Special Item List | ENG
BE |  |  |  |  | 50 | 007 | 001 | 00 | A4 | Manual Valves list | ENG
BE |  | x |  |  | 50 | 008 | 001 | 00 | A1 | Plant Side views BL - Plan d'interfaces | ENG |  |  |  | X |  | 28 | 2023-11-09 | 2023-11-09
BE |  |  |  |  | 50 | 201 | A | 00 | A4 | Requisition - Piping Works | ENG
|  |  |  | 51 | PIPING GENERAL ARRANGEMENT DRAWING | [5 empty] | ENG
BE | x | x |  |  | 51 | 1 | A | 00 | A1 | Piping general arrangement drawing | ENG
GS |  | x |  |  | 51 | 1 | 100 | 00 | A1 | Piping general arrangement drawing - Gazeifier Section GS | GS
OS |  | x |  |  | 51 | 1 | 200 | 00 | A1 | Piping general arrangement drawing - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | M | 136 | 51 | 1 | 300 | 00 | A1 | Piping general arrangement drawing - Boiler Section BS | BS
WO615 |  |  | M | 300 | 51 | 1 | 301 | 00 | A1 | PIPING PLAN AND SIDE VIEW
ES |  | x |  |  | 51 | 1 | 400 | 00 | A1 | Piping general arrangement drawing - Electrical Generation Section ES | ES
TS |  | x |  |  | 51 | 1 | 500 | 00 | A1 | Piping general arrangement drawing - Gaz Treatment Section TS | TS
US |  | x |  |  | 51 | 1 | 600 | 00 | A1 | Piping general arrangement drawing - Utilities Section US | US
BE |  |  |  |  | 51 | 002 | A | 00 | A1 | Piping rack arrangement drawing | ENG
BE |  |  |  |  | 51 | 3 | 001 | 00 | A1 | DWG - Safety Showers Routing | ENG
|  |  |  | 52 | ISOMETRICS | [5 empty] | ENG
BE |  | x |  |  | 52 | 001 | A | 00 | A3 | Isometrics list and isometrics | ENG
GS |  | x |  |  | 52 | 001 | 100 | 00 | A3 | Isometrics list and isometrics - Gazeifier Section GS | GS
OS |  | x |  |  | 52 | 001 | 200 | 00 | A3 | Isometrics list and isometrics - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | M | 320 | 52 | 001 | 300 | 00 | A3 | Isometrics list and isometrics - Boiler Section BS | BS
ES |  | x |  |  | 52 | 001 | 400 | 00 | A3 | Isometrics list and isometrics - Electrical Generation Section ES | ES
TS |  | x |  |  | 52 | 001 | 500 | 00 | A3 | Isometrics list and isometrics - Gaz Treatment Section TS | TS
US |  | x |  |  | 52 | 001 | 600 | 00 | A3 | Isometrics list and isometrics - Utilities Section US | US
BE |  |  |  |  | 52 | 002 | A | 00 | A3 | Steam Tracing- Isometrics list and isometrics | ENG
BE |  | x |  |  | 52 | 003 | A | 00 | A3 | Electrical tracing - Isometrics list and isometrics | ENG
|  |  |  | 53 | PIPING DETAIL - OTHER THAN ABOVE | [5 empty] | ENG
BE |  | x |  |  | 53 | 001 | A | 00 | A4 | List of Standard Piping Supports | ENG
|  | x |  |  | 53 | 001 | 101 | 00 | A4 | List of Standard Piping Supports - Gazeifier Section GS | GS
|  | x |  |  | 53 | 001 | 201 | 00 | A4 | List of Standard Piping Supports - Oxidizer and ashes Furnace Section OS | OS
|  | x |  |  | 53 | 001 | 301 | 00 | A4 | List of Standard Piping Supports - Boiler Section BS | BS
|  | x |  |  | 53 | 001 | 401 | 00 | A4 | List of Standard Piping Supports - Electrical Generation Section ES | ES
|  | x |  |  | 53 | 001 | 501 | 00 | A4 | List of Standard Piping Supports - Gaz Treatment Section TS | TS
BE |  | x |  |  | 53 | 002 | A | 00 | A4 | List of Special Piping Supports | ENG
|  | x |  |  | 53 | 002 | 101 | 00 | A4 | List of Special Piping Supports - Gazeifier Section GS | GS
|  | x |  |  | 53 | 002 | 201 | 00 | A4 | List of Special Piping Supports - Oxidizer and ashes Furnace Section OS | OS
|  | x |  |  | 53 | 002 | 301 | 00 | A4 | List of Special Piping Supports - Boiler Section BS | BS
|  | x |  |  | 53 | 002 | 401 | 00 | A4 | List of Special Piping Supports - Electrical Generation Section ES | ES
|  | x |  |  | 53 | 002 | 501 | 00 | A4 | List of Special Piping Supports - Gaz Treatment Section TS | TS
|  | x |  |  | 53 | 002 | A | 00 | A4 | List of Special Piping Supports - Utilities Section US | ENG
BE |  |  |  |  | 53 | 011 | 001 | 00 | A1 | DWG - Special Piping supports | ENG
[5 empty] | 53 | 011 | 101 | 00 | A1 | DWG - Special Piping supports - Gazeifier Section GS | GS
[5 empty] | 53 | 011 | 201 | 00 | A1 | DWG - Special Piping supports - Oxidizer and ashes Furnace Section OS | OS
[5 empty] | 53 | 011 | 301 | 00 | A1 | DWG - Special Piping supports - Boiler Section BS | BS
[5 empty] | 53 | 011 | 401 | 00 | A1 | DWG - Special Piping supports - Electrical Generation Section ES | ES
[5 empty] | 53 | 011 | 501 | 00 | A1 | DWG - Special Piping supports - Gaz Treatment Section TS | TS
[5 empty] | 53 | 011 | 601 | 00 | A1 | DWG - Special Piping supports - Utilities Section US | ENG
BE |  |  |  |  | 53 | 20 | 001 | 00 | A1 | DWG - Locations of Piping Supports | ENG
[5 empty] | 53 | 20 | 101 | 00 | A1 | DWG - Locations of Piping Supports - Gazeifier Section GS | GS
[5 empty] | 53 | 20 | 201 | 00 | A1 | DWG - Locations of Piping Supports - Oxidizer and ashes Furnace Section OS | OS
[5 empty] | 53 | 20 | 301 | 00 | A1 | DWG - Locations of Piping Supports - Boiler Section BS | BS
[5 empty] | 53 | 20 | 401 | 00 | A1 | DWG - Locations of Piping Supports - Electrical Generation Section ES | ES
[5 empty] | 53 | 20 | 501 | 00 | A1 | DWG - Locations of Piping Supports - Gaz Treatment Section TS | TS
[5 empty] | 53 | 20 | 601 | 00 | A1 | DWG - Locations of Piping Supports - Utilities Section US | ENG
WO615 |  | x |  |  | 53 | 30 | 300 | 00 | A4 | Piping Stress Calculation Note -Steam HP - boiler section | BS
WO615 |  | x |  |  | 53 | 30 | 300 | 00 | A4 | Piping Stress Calculation Note - Feed Water HP | BS
WO615 |  | x |  |  | 53 | 30 | 300 | 00 | A4 | Piping Stress Calculation Note - Steam LP | BS
BE |  | x |  |  | 53 | 30 | A | 00 | A4 | Piping Stress Calculation Note - Steam condensate | ENG
BE |  | x |  |  | 53 | 30 | A | 00 | A4 | Piping Stress Calculation Note - Steam LP - Elec prod. section | ENG
BE |  | x |  |  | 53 | 30 | A | 00 | A4 | Piping Stress Calculation Note - -Steam HP - Elec prod. section | ENG
|  |  |  | 54 | FIRE NETWORK AND OTHER BURIED | [5 empty] | ENG
|  |  |  | 56 | FITTINGS / VALVES | [5 empty] | ENG
BE |  |  |  |  | 56 | 001 | A | 00 | A4 | Material take off - Pipe, flange, fittings and valves | ENG
GS |  |  |  |  | 56 | 001 | 100 | 00 | A4 | Material take off - Pipe, flange, fittings and valves - Gazeifier Section GS | GS
OS |  |  |  |  | 56 | 001 | 200 | 00 | A4 | Material take off - Pipe, flange, fittings and valves - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 56 | 001 | 300 | 00 | A4 | Material take off - Pipe, flange, fittings and valves - Boiler Section BS | BS
ES |  |  |  |  | 56 | 001 | 400 | 00 | A4 | Material take off - Pipe, flange, fittings and valves - Electrical Generation Section ES | ES
TS |  |  |  |  | 56 | 001 | 500 | 00 | A4 | Material take off - Pipe, flange, fittings and valves - Gaz Treatment Section TS | TS
US |  |  |  |  | 56 | 001 | 600 | 00 | A4 | Material take off - Pipe, flange, fittings and valves - Utilities Section US | US
BE |  |  |  |  | 56 | 11 | A | 00 | A4 | Specification - Manual Valves | ENG
BE |  |  |  |  | 56 | 12 | A | 00 | A4 | Specification - Special Valves | ENG
BE |  |  |  |  | 56 | 14 | A | 00 | A4 | Specification - Spring Box | ENG
BE |  |  |  |  | 56 | 15 | A | 00 | A4 | Specification - Rotating Valves | ENG
BE |  |  |  |  | 56 | 16 | A | 00 | A4 | Specification - Valve Interlocks | ENG
BE |  |  |  |  | 56 | 20 | A | 00 | A4 | Requisition - Pipes and fittings | ENG
BE |  |  |  |  | 56 | 30 | A | 00 | A4 | Requisition - manual valves | ENG
BE |  |  |  |  | 56 | 40 | A | 00 | A4 | Requisition - Special valves | ENG
BE |  |  |  |  | 56 | 50 | A | 00 | A4 | Requisition - Spring box | ENG
BE |  |  |  |  | 56 | 60 | A | 00 | A4 | Requisition - Rotating valves | ENG
BE |  |  |  |  | 56 | 70 | A | 00 | A4 | Requisition - Valve Interlocks | ENG
BE |  |  |  |  | 56 | 80 |  | 00 |  | Drawing - Manual Valves | ENG
|  |  |  | 57 | Ducts / Gaines
|  | x |  |  | 57 | 1 | 001 | 0 | A1 | Guide drawing - Duct Layout Plan
|  | x |  |  | 57 | 2 | A | 00 | A1 | Generals / Details / supports DWG for Ducts
[5 empty] | 57 | 3 | A | 00 | A4 | Calculations notes for Ducts
[5 empty] | 57 | 4 | 100 | 00 | A1 | duct Drawings details and arrangement
WO615 |  |  | M | 530 | 57 | 4 | 301 | 00 | A1 | CONVECTIVA PASS - ECONOMIZER CONNECTING DUCT
WO615 |  |  | M | 534 | 57 | 4 | 302 | 00 | A1 | CONVECTIVA PASS - ECONOMIZER CONNECTING DUCT EXPANSION JOINT
WO615 |  |  | M | 591 | 57 |  |  |  |  | BOILER INLET DUCT
WO615 |  |  | M | 592 | 57 |  |  |  |  | BOILER INLET DUCT
[5 empty] | 57 | 10 | 200 | A | A4 | Requisition for ducts
[5 empty] | 57 | 11 | 200 | A | A4 | Specification for ducts
[5 empty] | 57 | 12 | 200 | A | A4 | Duct List (with process data)
|  |  |  | 58 | SAMPLE CONNECTION | [5 empty] | ENG
BE |  |  |  |  | 58 | 001 | A | 00 | A4 | List of sample connections with details and location | ENG
[5 empty] | 58 | 001 | 100 | 00 | A4 | List of sample connections with details and location
WO615 |  |  | hold | hold | 58 | 001 | 300 | 00 | A4 | List of sample connections with details and location
BE |  |  |  |  | 58 | 20 | A | 00 | A4 | Requisition | ENG
|  |  |  | 59 | MISCELLANEOUS | [5 empty] | ENG
BE |  |  |  |  | 59 | 001 | A | 00 | A4 | List of Tie-ins for erection and Site welds | ENG
GS |  |  |  |  | 59 | 001 | 100 | 00 | A4 | List of Tie-ins for erection and Site welds - Gazeifier Section GS | GS
OS |  |  |  |  | 59 | 001 | 200 | 00 | A4 | List of Tie-ins for erection and Site welds - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | P | 152 | 59 | 001 | 300 | 00 | A4 | List of Tie-ins for erection and Site welds - Boiler Section BS | BS
ES |  |  |  |  | 59 | 001 | 400 | 00 | A4 | List of Tie-ins for erection and Site welds - Electrical Generation Section ES | ES
TS |  |  |  |  | 59 | 001 | 500 | 00 | A4 | List of Tie-ins for erection and Site welds - Gaz Treatment Section TS | TS
US |  |  |  |  | 59 | 001 | 600 | 00 | A4 | List of Tie-ins for erection and Site welds - Utilities Section US | US
|  |  |  | 60 | INSTRUMENTATION | [5 empty] | ENG
INS | x | x |  |  | 60 | 001 | A | 00 | A3 | Instrument List with process data | ENG
GS |  | x |  |  | 60 | 001 | 100 | 00 | A3 | Instrument List with process data - Gazeifier Section GS | GS
OS |  | x |  |  | 60 | 001 | 200 | 00 | A3 | Instrument List with process data - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | S | 100 | 60 | 001 | 300 | 00 | A3 | Instrument List with process data - Boiler Section BS | BS
ES |  | x |  |  | 60 | 001 | 400 | 00 | A3 | Instrument List with process data - Electrical Generation Section ES | ES
TS |  | x |  |  | 60 | 001 | 500 | 00 | A3 | Instrument List with process data - Gaz Treatment Section TS | TS
INS |  |  |  |  | 60 | 002 | A | 00 | A3 | Level alarms and trip analysis - Instrumentation | ENG
INS |  | x |  |  | 60 | 003 | A | 00 | A4 | Hook up Drawings for instruments | ENG
GS |  | x |  |  | 60 | 003 | 100 | 00 | A4 | Hook up Drawings for instruments - Gazeifier Section GS | GS
OS |  | x |  |  | 60 | 003 | 200 | 00 | A4 | Hook up Drawings for instruments - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | S | 200 | 60 | 003 | 300 | 00 | A4 | Hook up Drawings for instruments - Boiler Section BS | BS
WO615 |  |  | S | 210 | 60 | 003 | 301 | 00 | A4 | SECONDARY PNEUMATIC HOOK UP
WO615 |  |  | S | 250 | 60 | 003 | 302 | 00 | A4 | PRIMARY & PNEUMATIC HOOK UP MATERIAL TAKE OFF
ES |  | x |  |  | 60 | 003 | 400 | 00 | A4 | Hook up Drawings for instruments - Electrical Generation Section ES | ES
TS |  | x |  |  | 60 | 003 | 500 | 00 | A4 | Hook up Drawings for instruments - Gaz Treatment Section TS | TS
US |  | x |  |  | 60 | 003 | 600 | 00 | A5 | Hook up Drawings for instruments - Utilities Section US | US
| x | Y |  | RFQ | 60 | 4 | A | 1 | A4 | General Specification for Instrumentation Design |  |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30 |  |  | 26 | 2023-03-19 | 2023-09-21
[5 empty] | 60 | 5 | A | 00 | A4 | Instrument layout
[5 empty] | 60 | 5 | 100 | 00 | A4 | Instrument layout
WO615 |  |  | S | 030 | 60 | 5 | 300 | 00 | A4 | Instrument layout with AIR DISTRIBUTION
WO615 |  |  | S | 310 | 60 | 6 | 300 | 00 | A4 | FIELD/JB INTERCONNECTION SCHEME
[5 empty] | 60 | 10 | 100 | 00 | A4 | Specification for instruments | Licensor
INS |  | x |  |  | 60 | 011 | A | 00 | A4 | Specification - Pressure gauges | ENG
INS |  | x |  |  | 60 | 012 | A | 00 | A4 | Specification - Temperature element | ENG
INS |  | x |  |  | 60 | 013 | A | 00 | A4 | Specification - Thermowell | ENG
WO615 |  |  | S | 505 | 60 | 013 | 301 | 00 | A4 | DATASHEET - THERMOELEMENTS AND THERMOWELLS
INS |  | x |  |  | 60 | 014 | A | 00 | A4 | Specification - Temperature gauges | ENG
WO615 |  |  | S | 510 | 60 | 14 | 301 | 00 | A4 | DATASHEET - TRANSMITTERS
INS |  | x |  |  | 60 | 015 | A | 00 | A4 | Specification - Pyrometer | ENG
INS |  | x |  |  | 60 | 016 | A | 00 | A4 | Specification - Level indicator (glass) | ENG
WO615 |  |  | S | 531 | 60 | 016 | 301 | 00 | A4 | DATASHEET- LOCAL GAUGES
INS |  | x |  |  | 60 | 017 | A | 00 | A4 | Specification - Level indicator (Magnetics) | ENG
WO615 |  |  | S | 531 | 60 | 017 | 301 | 00 | A4 | DATASHEET - LEVEL GAUGES
INS |  | x |  |  | 60 | 018 | A | 00 | A4 | Specification - Level Transmitters (Radar) | ENG
INS |  | x |  |  | 60 | 019 | A | 00 | A4 | Specification - Differential pressure transmitters | ENG
INS |  | x |  |  | 60 | 020 | A | 00 | A4 | Specification - Rotameters | ENG
INS |  | x |  |  | 60 | 021 | A | 00 | A4 | Specification - Coriolis Flow Meter | ENG
INS |  | x |  |  | 60 | 022 | A | 00 | A4 | Specification - Orifice plates | ENG
WO615 |  |  | S | 500 | 60 | 022 | 301 | 00 | A4 | DATASHEET - PRIMARY FLOW ELEMENTS
INS |  | x |  |  | 60 | 023 | A | 00 | A4 | Specification - Restriction orifice | ENG
INS |  | x |  |  | 60 | 024 | A | 00 | A4 | Specification - Rupture disc | ENG
INS |  | x |  |  | 60 | 37 | A | 00 | A4 | Specification - Flushing panel | ENG
INS |  | x |  |  | 60 | 026 | A | 00 | A4 | Specification - Safety valves | ENG
WO615 |  |  | P | 507 | 60 | 026 | 301 | 00 | A4 | DATASHEET - Safety VALVES
INS |  | x |  |  | 60 | 027 | A | 00 | A4 | Specification - Control valves | ENG
[5 empty] | 60 | 027 | 101 | 00 | A4 | List - CONTROL VALVES
[5 empty] | 60 | 027 | 102 | 00 | A4 | DATASHEET - CONTROL VALVES
WO615 |  |  | S | 590 | 60 | 027 | 301 | 00 | A4 | DATASHEET - PNEUMATIC CONTROL VALVES
INS |  | x |  |  | 60 | 028 | 301 | 00 | A4 | Specification - ON/OFF Valves | ENG
WO615 |  |  | S | 570 | 60 | 028 | A | 00 | A4 | DATASHEET- ON/OFF PNEUMATIC VALVES
INS |  | x |  |  | 60 | 029 | A | 00 | A4 | Specification - Regulators and self-regulating valves | ENG
INS |  | x |  |  | 60 | 030 | A | 00 | A4 | Specification - Gas detector | ENG
INS |  | x |  |  | 60 | 031 | A | 00 | A4 | Specification - Flame scanners | ENG
INS |  | x |  |  | 60 | 032 | A | 00 | A4 | Specification - Vibrating blades level | ENG
INS |  | x |  |  | 60 | 033 | A | 00 | A4 | Specification - Jacketed Control valves | ENG
INS |  | x |  |  | 60 | 034 | A | 00 | A4 | Specification - Special Control valves | ENG
INS |  | x |  |  | 60 | 035 | A | 00 | A4 | Specification - Jacketed ON/OFF valves | ENG
INS |  | x |  |  | 60 | 036 | A | 00 | A4 | Specification - THERMAL MASS FLOWMETER | ENG
INS |  | x |  |  | 60 | 037 | A | 00 | A4 | Specification - Special Jacketed control valves | ENG
INS |  | x |  |  | 60 | 038 |  | 00 |  | Specification - Jacketed manual valves | ENG
WO615 |  |  | S | 575 | 60 | 039 | 300 | 0 | A4 | DATASHEET - MOTOR OPERATED VALVES
INS |  | x |  |  | 60 | 040 | A | 00 | A4 | Specification - TDS Analyzers | ENG
INS |  | x |  |  | 60 | 50 | A | 00 | A4 | Specification - Conductivity Analyzer | ENG
INS |  | x |  |  | 60 | 51 | A | 00 | A4 | Specification - CEMS Analyzer | ENG
TS |  |  |  |  | 60 | 52 | 500 | 00 | A1 | Drawing - CEMS Analyzer | TS
|  |  |  | 62 | CONTROL ROOM LAYOUT | [5 empty] | ENG
SYST |  | x |  |  | 62 | 1 | A | 00 | A1 | New Cogeneration Unit Station - layout | ENG
ES |  | x |  |  | 62 | 1 | 400 | 00 | A1 | New Cogeneration Unit Station - layout - Electrical Generation Section ES | ES
ELE |  | x |  |  | 62 | 1 | 600 | 00 | A1 | New Cogeneration Unit Station - layout - Utilities Section US | US
SYST |  | x |  |  | 62 | 2 | A | 00 | A1 | New Cogeneration Unit Station - MCC | ENG
ES |  | x |  |  | 62 | 2 | 400 | 00 | A1 | New Cogeneration Unit Station - MCC - Electrical Generation Section ES | ES
ELE |  | x |  |  | 62 | 2 | 600 | 00 | A1 | New Cogeneration Unit Station - MCC - Electrical Generation Section ES | US
SYST |  | x |  |  | 62 | 3 | A | 00 | A1 | New Cogeneration Unit Station - CTRL Room | ENG
ES |  | x |  |  | 62 | 3 | 400 | 00 | A1 | New Cogeneration Unit Station - CTRL Room - Electrical Generation Section ES | ES
ELE |  | x |  |  | 62 | 3 | 600 | 00 | A1 | New Cogeneration Unit Station - CTRL Room - Utilities Section US | US
|  |  |  | 63 | EQUIPEMENTS DES ARMOIRES ET COFFRETS LOCAUX
[5 empty] | 63 | 001 | 101 | 00 | A3 | Electrical cabinet for xx | GS
[5 empty] | 63 | 10 | 101 | 00 | A3 | Wiring diagram | GS
|  |  |  | 65 | EARTHING CONNECTIONS | [5 empty] | ENG
ELEC |  | x |  |  | 65 | 001 | 001 | 00 | A1 | Plan d'interface pour mise à la Terre de l'unité | ENG |  |  | X |  |  | 20 | 2023-07-21 | 2023-07-21
GS |  | x |  |  | 65 | 001 | 100 | 00 | A1 | EARTHING - Grid Connections - Gazeifier Section GS | GS
OS |  | x |  |  | 65 | 001 | 200 | 00 | A1 | EARTHING - Grid Connections - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 65 | 001 | 300 | 00 | A1 | EARTHING - Grid Connections - Boiler Section BS | BS
ES |  | x |  |  | 65 | 001 | 400 | 00 | A1 | EARTHING - Grid Connections - Electrical Generation Section ES | ES
TS |  | x |  |  | 65 | 001 | 500 | 00 | A1 | EARTHING - Grid Connections - Gaz Treatment Section TS | TS
US |  | x |  |  | 65 | 001 | 600 | 00 | A1 | EARTHING - Grid Connections - Utilities Section US | US
|  |  |  | 66 | ELECTRICAL POWER | [5 empty] | ENG
| x | Y |  | RFQ | 66 | 001 | A | 1 | A4 | Electrical Design Basis | ENG |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30 |  |  | 18 | 2023-07-20 | 2023-07-20
PGO |  |  |  |  | 66 | 002 | 400 | 1 | A4 | Requisition for Electrical HTA | ENG | [6 empty] | 2023-04-14 |  |  |  |  | 2023-04-14
MED |  |  |  |  | 66 | 003 | 400 | 1 | A4 | Specification for Electrical HTA | ENG | [6 empty] | 2023-04-16 |  |  |  |  | 2023-07-19
PGO |  |  |  |  | 66 | 4 | 400 | 00 | A4 | Requisition for Electrical HTA TRANSFORMERs | ENG | [6 empty] | 2023-04-21
MED |  |  |  |  | 66 | 5 | 400 | 00 | A4 | Spécification for TR-401 TR-403 & TR 404 | ENG
MED |  |  |  |  | 66 | 5 | 401 | 00 | A4 | Spécification for TR-401 Generator Transformer | ENG | [6 empty] | 2023-04-23 |  |  |  | cancelled
MED |  |  |  |  | 66 | 5 | 403 | 00 | A4 | Spécification for TR-403 DistributionTransformer | ENG | [6 empty] | 2023-04-23 |  |  |  | cancelled
MED |  |  |  |  | 66 | 5 | 404 | 00 | A4 | Spécification for TR-404 Auxiliary Transformer | ENG | [6 empty] | 2023-04-27 |  |  |  | cancelled
[5 empty] | 66 | 6 | 400 | 00 | A4 | Requisition and specifications for Electrical HTA TRANSFORMERs CANCELED
ELE | x | x |  |  | 66 | 10 | A | 00 | A4 | Bilan de puissance | ENG | [5 empty] | 23 | 2023-08-22 | 2023-08-25
GS |  | x |  |  | 66 | 10 | 100 | 0 | A4 | Electrical Consumer list - Gazeifier Section GS | GS
OS |  | x |  |  | 66 | 10 | 200 | 00 | A4 | Electrical Consumer list - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | E | 100 | 66 | 10 | 300 | 00 | A4 | Electrical Consumer list - Boiler Section BS | BS
ES |  | x |  |  | 66 | 10 | 400 | 00 | A4 | Electrical Consumer list - Electrical Generation Section ES | ES
TS |  | x |  |  | 66 | 10 | 500 | 00 | A4 | Electrical Consumer list - Gaz Treatment Section TS | TS
US |  | x |  |  | 66 | 10 | 600 | 00 | A4 | Electrical Consumer list - Utilities Section US | US
ELE | x | x |  |  | 66 | 20 | A | 1 | A3 | Single Line Diagram UNIFILAIRE DE DISTRIBUTION | ENG |  |  |  | X |  | 14 | 2023-06-30 | 2023-06-30 |  |  | 16 | 2023-07-18 | 2023-07-19 |  | 2023-07-20
GS |  | x |  |  | 66 | 20 | 100 | 00 | A4 | Single Line Diagram LV - Gazeifier Section GS | GS
OS |  | x |  |  | 66 | 20 | 200 | 00 | A4 | Single Line Diagram LV - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 66 | 20 | 300 | 00 | A4 | Single Line Diagram LV - Boiler Section BS | BS
ES |  | x |  |  | 66 | 20 | 400 | 00 | A4 | Single Line Diagram LV - Electrical Generation Section ES | ES
TS |  | x |  |  | 66 | 20 | 500 | 00 | A4 | Single Line Diagram LV - Gaz Treatment Section TS | TS
US |  | x |  |  | 66 | 20 | 600 | 00 | A4 | Single Line Diagram LV - Utilities Section US | US
[5 empty] | 66 | 21 | 400 | 00 | A4 | Requisition for power distribution
[5 empty] | 66 | 22 | 401 | 00 | A4 | Electrical cabinet for power distribution
ELE | x | x |  |  | 66 | 30 | 001 | 2 | A3 | SCHEMA DE PRODUCTION | ENG |  |  |  | X |  | 14 | 2023-06-30 | 2023-06-30 |  |  | 19 | 2023-07-20 | 2023-07-20 |  | 2023-07-20
ES |  |  |  |  | 66 | 30 | 400 | 00 | A4 | Single Line Diagram HV - Electrical Generation Section ES | ES
US |  |  |  |  | 66 | 30 | 600 | 00 | A4 | Single Line Diagram HV - Utilities Section US | US
ELE |  | x |  |  | 66 | 40 | A | 00 | A4 | Electrical Power Calculations | ENG
GS |  | x |  |  | 66 | 40 | 100 | 00 | A4 | Electrical Power Calculations - Gazeifier Section GS | GS
OS |  | x |  |  | 66 | 40 | 200 | 00 | A4 | Electrical Power Calculations - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 66 | 40 | 300 | 00 | A4 | Electrical Power Calculations - Boiler Section BS | BS
ES |  | x |  |  | 66 | 40 | 400 | 00 | A4 | Electrical Power Calculations - Electrical Generation Section ES | ES
TS |  | x |  |  | 66 | 40 | 500 | 00 | A4 | Electrical Power Calculations - Gaz Treatment Section TS | TS
US |  | x |  |  | 66 | 40 | 600 | 00 | A4 | Electrical Power Calculations - Utilities Section US | US
WO615 |  |  | E | 510 | 66 | 50 | 300 | 00 | A4 | DATASHEET - ELECTRICAL MOTORS
WO615 |  |  | E | 001 | 66 | 60 | 300 | 00 | A4 | ELECTRICAL LAYOUT INTERFACE DWG.
WO615 |  |  | S | 260 | 66 | 70 | 300 | 00 | A4 | ELECTRIC MATERIAL TAKE OFF
|  |  |  | 67 | LIGHTING | [5 empty] | ENG
ELE |  | x |  |  | 67 | 1 | A | 00 | A4 | Lighting Calculations note | ENG
GS |  | x |  |  | 67 | 1 | 100 | 00 | A4 | Lighting Calculations note - Gazeifier Section GS | GS
OS |  | x |  |  | 67 | 1 | 200 | 00 | A4 | Lighting Calculations note - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 67 | 1 | 300 | 00 | A4 | Lighting Calculations note - Boiler Section BS | BS
ES |  | x |  |  | 67 | 1 | 400 | 00 | A4 | Lighting Calculations note - Electrical Generation Section ES | ES
TS |  | x |  |  | 67 | 1 | 500 | 00 | A4 | Lighting Calculations note - Gaz Treatment Section TS | TS
US |  | x |  |  | 67 | 1 | 600 | 00 | A4 | Lighting Calculations note - Utilities Section US | US
ELE |  | x |  |  | 67 | 2 | A | 00 | A1 | Lighting Aarrangment | ENG
GS |  | x |  |  | 67 | 2 | 100 | 00 | A1 | Lighting Aarrangment - Gazeifier Section GS | GS
OS |  | x |  |  | 67 | 2 | 200 | 00 | A1 | Lighting Aarrangment - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 67 | 2 | 300 | 00 | A1 | Lighting Aarrangment - Boiler Section BS | BS
ES |  | x |  |  | 67 | 2 | 400 | 00 | A1 | Lighting Aarrangment - Electrical Generation Section ES | ES
TS |  | x |  |  | 67 | 2 | 500 | 00 | A1 | Lighting Aarrangment - Gaz Treatment Section TS | TS
US |  | x |  |  | 67 | 2 | 600 | 00 | A1 | Lighting Aarrangment - Utilities Section US | US
|  |  |  | 69 | CABLE ROUTING | [5 empty] | ENG
ELE |  | x |  |  | 69 | 1 | A | 00 | A4 | Cable routing & trays for Elec / Instrum with sections and instrument tags | ENG
GS |  | x |  |  | 69 | 1 | 100 | 00 | A4 | Cable routing & trays for Elec / Instrum - Gazeifier Section GS | GS
OS |  | x |  |  | 69 | 1 | 200 | 00 | A4 | Cable routing & trays for Elec / Instrum - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | S | 020 | 69 | 1 | 300 | 00 | A4 | Cable routing & trays for Elec / Instrum - Boiler Section BS | BS
ES |  | x |  |  | 69 | 1 | 400 | 00 | A4 | Cable routing & trays for Elec / Instrum - Electrical Generation Section ES | ES
TS |  | x |  |  | 69 | 1 | 500 | 00 | A4 | Cable routing & trays for Elec / Instrum - Gaz Treatment Section TS | TS
US |  | x |  |  | 69 | 1 | 600 | 00 | A4 | Cable routing & trays for Elec / Instrum - Utilities Section US | US
|  | x |  |  | 69 | 2 | 600 | 00 | A4 | Coupe et pénétrations de câbles dans local technique
|  |  |  | 72 | CABLE LIST | [5 empty] | ENG
ELE |  | x |  |  | 72 | 1 | A | 00 | A4 | Cable List HV / LV | ENG
GS |  | x |  |  | 72 | 001 | 100 | 00 | A4 | Cable List HV / LV - Gazeifier Section GS | GS
OS |  | x |  |  | 72 | 001 | 200 | 00 | A4 | Cable List HV / LV - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 72 | 001 | 300 | 00 | A4 | Cable List HV / LV - Boiler Section BS | BS
ES |  | x |  |  | 72 | 001 | 400 | 00 | A4 | Cable List HV / LV - Electrical Generation Section ES | ES
TS |  | x |  |  | 72 | 001 | 500 | 00 | A4 | Cable List HV / LV - Gaz Treatment Section TS | TS
US |  | x |  |  | 72 | 001 | 600 | 00 | A4 | Cable List HV / LV - Utilities Section US | US
ELE |  | x |  |  | 72 | 2 | A | 00 | A4 | Cable Calculation HV / LV | ENG
GS |  | x |  |  | 72 | 2 | 100 | 00 | A4 | Cable Calculation HV / LV - Gazeifier Section GS | GS
OS |  | x |  |  | 72 | 2 | 200 | 00 | A4 | Cable Calculation HV / LV - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 72 | 2 | 300 | 00 | A4 | Cable Calculation HV / LV - Boiler Section BS | BS
ES |  | x |  |  | 72 | 2 | 400 | 00 | A4 | Cable Calculation HV / LV - Electrical Generation Section ES | ES
TS |  | x |  |  | 72 | 2 | 500 | 00 | A4 | Cable Calculation HV / LV - Gaz Treatment Section TS | TS
US |  | x |  |  | 72 | 2 | 600 | 00 | A4 | Cable Calculation HV / LV - Utilities Section US | US
[5 empty] | 72 | 2 | A | 00 | A4
[5 empty] | 72 | 2 | 100 | 00 | A4 | INSTRUMENT CABLE LIST | GS
WO615 |  |  | S | 130 | 72 | 2 | 300 | 00 | A4 | INSTRUMENT CABLE LIST
|  |  |  | 73 | TRACAGE ELECTRIQUE
[5 empty] | 74 | 1 | 100 | 00 | A4 | Heat Tracing | GS
|  |  |  | 74 | SYSTEMS | [5 empty] | ENG
|  | x |  |  | 74 | 1 | A | 00 | A4 | I/O list
GS |  | x |  |  | 74 | 1 | 100 | 00 | A4 | I/O list - Gazeifier Section GS | GS
OS |  | x |  |  | 74 | 1 | 200 | 00 | A4 | I/O list - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | na |  | 74 | 1 | 300 | 00 | A4 | I/O list - Boiler Section BS | BS
ES |  | x |  |  | 74 | 1 | 400 | 00 | A4 | I/O list - Electrical Generation Section ES | ES
TS |  | x |  |  | 74 | 1 | 500 | 00 | A4 | I/O list - Gaz Treatment Section TS | TS
US |  | x |  |  | 74 | 1 | 600 | 00 | A4 | I/O list - Utilities Section US | US
|  | x |  |  | 74 | 2 | A | 00 | A4 | Functional analysis and description
GS |  | x |  |  | 74 | 2 | 100 | 00 | A4 | Functional analysis and description - Gazeifier Section GS | GS
OS |  | x |  |  | 74 | 2 | 200 | 00 | A4 | Functional analysis and description - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | S | 620 | 74 | 2 | 300 | 00 | A4 | Functional analysis and description - Boiler Section BS | BS
ES |  | x |  |  | 74 | 2 | 400 | 00 | A4 | Functional analysis and description - Electrical Generation Section ES | ES
TS |  | x |  |  | 74 | 2 | 500 | 00 | A4 | Functional analysis and description - Gaz Treatment Section TS | TS
US |  | x |  |  | 74 | 2 | 600 | 00 | A4 | Functional analysis and description - Utilities Section US | US
|  | x |  |  | 74 | 3 | A | 00 | A4 | Cause and Effect Diagram
GS |  | x |  |  | 74 | 3 | 100 | 00 | A4 | Cause and Effect Diagram - Gazeifier Section GS | GS
OS |  | x |  |  | 74 | 3 | 200 | 00 | A4 | Cause and Effect Diagram - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 74 | 3 | 300 | 00 | A4 | Cause and Effect Diagram - Boiler Section BS | BS
ES |  | x |  |  | 74 | 3 | 400 | 00 | A4 | Cause and Effect Diagram - Electrical Generation Section ES | ES
TS |  | x |  |  | 74 | 3 | 500 | 00 | A4 | Cause and Effect Diagram - Gaz Treatment Section TS | TS
US |  |  |  |  | 74 | 3 | 600 | 00 | A4 | Cause and Effect Diagram - Utilities Section US | US
|  | x |  |  | 74 | 4 | A | 00 | A4 | Systems Architecture
GS |  | x |  |  | 74 | 4 | 100 | 00 | A4 | Systems Architecture - Gazeifier Section GS | GS
OS |  | x |  |  | 74 | 4 | 200 | 00 | A4 | Systems Architecture - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 74 | 4 | 300 | 00 | A4 | Systems Architecture - Boiler Section BS | BS
ES |  | x |  |  | 74 | 4 | 400 | 00 | A4 | Systems Architecture - Electrical Generation Section ES | ES
TS |  | x |  |  | 74 | 4 | 500 | 00 | A4 | Systems Architecture - Gaz Treatment Section TS | TS
US |  |  |  |  | 74 | 4 | 600 | 00 | A4 | Systems Architecture - Utilities Section US | US
[5 empty] | 74 | 1 | 600 | 0 | A4 | Requisition for PLC System | ENG
[5 empty] | 74 | 2 | 600 | 0 | A4 | PLC Specification | ENG
|  |  |  | 78 | LOOP DIAGRAM | [5 empty] | ENG
INS |  | x |  |  | 78 | 001 | A | 00 | A3 | Instrument Loop Diagrams | ENG
GS |  | x |  |  | 78 | 001 | 100 | 00 | A3 | Instrument Loop Diagrams - Gazeifier Section GS | GS
OS |  | x |  |  | 78 | 001 | 200 | 00 | A3 | Instrument Loop Diagrams - Oxidizer and ashes Furnace Section OS | OS
[5 empty] | 78 | 001 | 300 | 00 | A3 | Instrument Loop Diagrams - Boiler Section BS | BS
ES |  | x |  |  | 78 | 001 | 400 | 00 | A3 | Instrument Loop Diagrams - Electrical Generation Section ES | ES
TS |  | x |  |  | 78 | 001 | 500 | 00 | A3 | Instrument Loop Diagrams - Gaz Treatment Section TS | TS
US |  |  |  |  | 78 | 001 | 600 | 00 | A3 | Instrument Loop Diagrams - Utilities Section US | US
|  |  |  | 79 | TROUBLESHOOTING DIAGRAM | [5 empty] | ENG
Ins | x | x |  |  | 79 | 001 | A | 00 | A4 | Troubleshooting diagrams | ENG
[5 empty] | 79 | 001 | 100 | 00 | A4 | Wiring & Troubleshooting diagrams | GS
WO615 |  | x | hold | hold | 79 | 001 | 300 | 00 | A3 | Instrument JB details (trouble shooting diagram)
[5 empty] | 79 | 10 | 100 | 00 | A3 | Instrument JB details (trouble shooting diagram) | GS
|  |  |  | 80 | PACKAGE | [5 empty] | ENG
PGO |  |  |  |  | 80 | 001 | A | 00 | A4 | Requisition for | ENG
PGO |  |  |  | RFQ | 80 | 001 | 100 | 00 | A4 | Requisition for - Gazeifier Section GS | GS
PGO |  |  |  |  | 80 | 001 | 200 | 00 | A4 | Requisition for - Oxidizer and ashes Furnace Section OS | OS
PGO |  |  |  |  | 80 | 001 | 300 | 1 | A4 | Requisition for - Boiler Section BS | BS | [6 empty] | 2023-03-23
PGO |  |  |  |  | 80 | 001 | 400 | 00 | A4 | Requisition for - Electrical Generation Section ES | ES
PGO |  |  |  |  | 80 | 001 | 500 | 00 | A4 | Requisition for - Gaz Treatment Section TS | [7 empty] | 2023-04-03
PGO |  |  |  |  | 80 | 2 | A | 00 | A4 | Specification for | ENG
PGO |  |  |  | RFQ | 80 | 2 | 100 | 00 | A4 | Specification for - Gazeifier Section GS | GS
PGO |  |  |  |  | 80 | 2 | 200 | 00 | A4 | Specification for - Oxidizer and ashes Furnace Section OS | OS
PGO |  |  |  |  | 80 | 2 | 300 | 0 | A4 | Specification for - Boiler Section BS | BS | [6 empty] | 2023-03-22
PGO |  |  |  |  | 80 | 2 | 400 | 00 | A4 | Specification for - Electrical Generation Section ES | ES | [6 empty] | 2023-04-06
PGO |  |  |  |  | 80 | 2 | 500 | 00 | A4 | Specification for - Flue Gaz Treatment Section TS | [7 empty] | 2023-04-03
PGO |  |  |  |  | 80 | 3 | A | 00 | A4 | Technical Bid Tabulation for | ENG
GS |  |  |  | RFQ | 80 | 3 | 100 | 00 | A4 | Technical Bid Tabulation for - Gazeifier Section GS | GS
OS |  |  |  |  | 80 | 3 | 200 | 00 | A4 | Technical Bid Tabulation for - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 80 | 3 | 300 | 00 | A4 | Technical Bid Tabulation for - Boiler Section BS | BS
ES |  |  |  |  | 80 | 3 | 400 | 00 | A4 | Technical Bid Tabulation for - Electrical Generation Section ES | ES
TS |  |  |  |  | 80 | 3 | 500 | 00 | A4 | Technical Bid Tabulation for - Gaz Treatment Section TS | TS
Prec. |  |  |  |  | 80 | 5 | A | 00 | A1 |  | ENG
GS |  |  |  |  | 80 | 5 | 100 | 00 | A1 |  | GS
OS |  |  |  |  | 80 | 5 | 200 | 00 | A1 |  | OS
BS |  |  |  |  | 80 | 5 | 300 | 00 | A1 |  | BS
ES |  |  |  |  | 80 | 5 | 400 | 00 | A1 |  | ES
TS |  |  |  |  | 80 | 5 | 500 | 00 | A1 |  | TS
[5 empty] | 80 | 401 | A | 0 | A4 | PDS GTA | [7 empty] | 2023-04-12
[5 empty] | 80 | 501 | A | 0 | A4 | PDS Flue Gas Treatment | [7 empty] | 2023-04-06
|  |  |  | 81 | INSULATION | [5 empty] | ENG
PGO | x | Y |  | RFQ | 81 | 001 | A | 00 | A4 | Insulation general specification | ENG |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30
Proce |  |  |  |  | 81 | 10 | A | 00 | A4 | List of insulated piping Line | ENG
GS |  |  |  |  | 81 | 10 | 100 | 00 | A4 | List of insulated piping Line - Gazeifier Section GS | GS
OS |  |  |  |  | 81 | 10 | 200 | 00 | A4 | List of insulated piping Line - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | M | 611 | 81 | 10 | 300 | 00 | A4 | List of insulated piping Line - Boiler Section BS | BS
ES |  |  |  |  | 81 | 10 | 400 | 00 | A4 | List of insulated piping Line - Electrical Generation Section ES | ES
TS |  |  |  |  | 81 | 10 | 500 | 00 | A4 | List of insulated piping Line - Gaz Treatment Section TS | TS
US |  |  |  |  | 81 | 10 | 600 | 00 | A4 | List of insulated piping Line - Utilities Section US | US
Proce |  |  |  |  | 81 | 5 | A | 00 | A4 | List of insulated equipments | ENG
GS |  |  |  |  | 81 | 5 | 100 | 00 | A4 | List of insulated equipments - Gazeifier Section GS | GS
OS |  |  |  |  | 81 | 5 | 200 | 00 | A4 | List of insulated equipments - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 81 | 5 | 300 | 00 | A4 | List of insulated equipments - Boiler Section BS | BS
WO615 |  |  | M | 600 | 81 | 5 | 301 | 00 |  | BOILER INSULATION GENERAL ASSEMBLY DRAWING
WO615 |  |  | M | 601 | 81 | 5 | 302 | 00 |  | INSULATION TYPICAL DRAWING
WO615 |  |  | M | 605 | 81 | 5 | 303 | 00 |  | GAS DUCT INSULATION DRAWING
WO615 |  |  | M | 606 | 81 | 5 | 304 | 00 |  | GAS DUCT INSULATION TYPICAL
WO615 |  |  | M | 609 | 81 | 5 | 305 | 00 |  | INSULATION DRAWING FOR DEHAERATOR AND BLOW DOWN
ES |  |  |  |  | 81 | 5 | 400 | 00 | A4 | List of insulated equipments - Electrical Generation Section ES | ES
TS |  |  |  |  | 81 | 5 | 500 | 00 | A4 | List of insulated equipments - Gaz Treatment Section TS | TS
US |  |  |  |  | 81 | 5 | 600 | 00 | A4 | List of insulated equipments - Utilities Section US | US
|  |  |  | 82 | PAINTING | [5 empty] | ENG
PGO | x | Y |  | RFQ | 82 | 001 | A | 1 | A4 | Painting specification | ENG |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30 |  |  | 26 | 2023-09-19 | 2023-09-19
|  |  |  | 84 | NOBO
| x | x |  | RFQ | 84 | 001 | A | 00 | A4 | Specification for PED application |  |  |  | X |  |  | 4 | 2023-03-15 | 2023-05-10
| x | x |  |  | 85 | 002 | A |  | A5 | PED, ATEX and CE conformity
[5 empty] | 84 | 3 | A |  | A6 | Requisition - PED and ATEX integration
PGO |  |  |  |  | 84 | 10 | A | 00 | A4 | Requisition - PED and ATEX integration | ENG
|  |  |  | 85 | SITE | [5 empty] | ENG
site |  | x |  | RFQ | 85 | 001 | A | 00 | A4 | Site Organisation Plan | ENG | [6 empty] | 2023-03-30
site |  | ? |  |  | 85 | 002 | A | 00 | A4 | Working site regulation | ENG
site | x | x |  |  | 85 | 003 | 001 | 2 | A1 | Plan d'impantation Chantier Clos | ENG | [5 empty] | Propal | 2023-04-24 |  |  |  | 31 | 2023-12-13 | 2023-12-13
site |  |  |  |  | 85 | 004 | 001 | 00 | A1 | SITE management plan | ENG
site |  |  |  |  | 85 | 005 | 001 | 00 | A1 | Site organization | ENG
[5 empty] | 85 | 6 | 001 | 00 | A4 | Requirements for Site activities
GS |  |  |  |  | 85 | 6 | 100 | 00 | A4 | Requirements for Site activities - Gazeifier Section GS | GS
OS |  |  |  |  | 85 | 6 | 200 | 00 | A4 | Requirements for Site activities - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | hold | hold | 85 | 6 | 300 | 00 | A4 | Requirements for Site activities - Boiler Section BS | BS
ES |  |  |  |  | 85 | 6 | 400 | 00 | A4 | Requirements for Site activities - Electrical Generation Section ES | ES
TS |  |  |  |  | 85 | 6 | 500 | 00 | A4 | Requirements for Site activities - Gaz Treatment Section TS | TS
US |  |  |  |  | 85 | 6 | 600 | 00 | A4 | Requirements for Site activities - Utilities Section US | US
site |  |  |  |  | 85 | 10 | A | 00 | A4 | Requisition - Site logistics | ENG
|  |  |  | 86 | EQUIPMENT INSTALLATION | [5 empty] | ENG
Site |  | ? |  |  | 86 | 001 | A | 00 | A4 | requirements for equipment erection | ENG
Site |  | x |  |  | 86 | 2 | A | 00 | A4 | Site erection sequence | ENG
GS |  | x |  |  | 86 | 2 | 100 | 00 | A4 | Site erection sequence - Gazeifier Section GS | GS
OS |  | x |  |  | 86 | 2 | 200 | 00 | A4 | Site erection sequence - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | C | 010 | 86 | 2 | 300 | 00 | A4 | Site erection sequence - Boiler Section BS | BS
ES |  | x |  |  | 86 | 2 | 400 | 00 | A4 | Site erection sequence - Electrical Generation Section ES | ES
TS |  | x |  |  | 86 | 2 | 500 | 00 | A4 | Site erection sequence - Gaz Treatment Section TS | TS
Site |  | x |  |  | 86 | 3 | A | 00 | A4 | Constructability Reviews | ENG
GS |  | x |  |  | 86 | 3 | 100 | 00 | A4 | Constructability Reviews - Gazeifier Section GS | GS
OS |  | x |  |  | 86 | 3 | 200 | 00 | A4 | Constructability Reviews - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 86 | 3 | 300 | 00 | A4 | Constructability Reviews - Boiler Section BS | BS
ES |  | x |  |  | 86 | 3 | 400 | 00 | A4 | Constructability Reviews - Electrical Generation Section ES | ES
TS |  | x |  |  | 86 | 3 | 500 | 00 | A4 | Constructability Reviews - Gaz Treatment Section TS | TS
[5 empty] | 86 | 4 | 300 | 00 | A4 | Maintenance sequence of boiler pressure parts
|  |  |  | 87 | SOIL ANALYSIS | [5 empty] | ENG
|  |  |  | 88 | STANDARD | [5 empty] | ENG
PGO | x | x |  | RFQ | 88 | 001 | A | 00 | A4 | STD Pressure equipment | ENG |  |  | X |  |  | 4 | 2021-07-27 | 2023-05-10
PGO | x | x |  | RFQ | 88 | 002 | A | 00 | A4 | Standard Construction - Piping | ENG |  |  | X |  |  | 4 | 2010-06-04 | 2023-05-10
PGO | x | Y |  | RFQ | 88 | 3 | A | 00 | A4 | Specification for Pressure and Atm Equipment | ENG |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30
PGO | x | x |  | RFQ | 88 | 004 | A | 00 | A4 | STD for Steam tracing | ENG |  |  | X |  |  | 4 | 2021-07-27 | 2023-05-10
PGO | x | x |  | RFQ | 88 | 005 | A | 00 | A4 | Standard Construction - Piping supports | ENG |  |  | X |  |  | 4 | 2021-07-27 | 2023-05-10
PGO | x | x |  | RFQ | 88 | 006 | A | 00 | A4 | Standard Construction - Steel Structure | ENG |  |  | X |  |  | 4 | 2021-07-27 | 2023-05-10
BE | x | x |  | RFQ | 88 | 7 | A | 00 | A4 | Standard Construction - Civil Work | ENG |  |  | X |  |  | 4 | 2021-07-23 | 2023-05-10
PGO | x | Y |  | RFQ | 88 | 8 | A | 00 | A4 | Rotating Machinery and Package Unit | ENG
PGO | x | x |  | RFQ | 88 | 9 | A | 00 | A4 | DESIGN RULES FOR FOUNDATION, STRUCTURE AND BUILDING | ENG |  |  | X |  |  | 4 | 2023-03-15 | 2023-05-10
PGO | x | Y |  | RFQ | 88 | 10 | A | 0 | A4 | Specification for Plastic Items & Vessels | ENG |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30
PGO | x | x |  | RFQ | 88 | 11 | A | 0 | A4 | Standard Instrument Hook up |  |  |  | X |  |  | 4 | 2022-08-30 | 2023-05-10
PGO | x | Y |  | RFQ | 88 | 12 | A | 1 | A4 | General specification for layout and piping design | ENG |  |  | X |  |  | 8 | 2023-03-15 | 2023-05-30 |  |  | 26 | 2023-09-09 | 2023-09-21
|  | x |  |  | 88 | 13 | A | 0 | A4 | Standards for Elec and Instrum (including CEM protection)
|  |  |  | 89 | HSE | [5 empty] | ENG
HSE | x | x |  | RFQ | 89 | 001 | A | 01 | A4 | HSE PLAN | ENG |  |  | X | [7 empty] | 7 | 2023-05-24 | 2023-05-29
ALL | x | x |  |  | 89 | 002 | A | 00 | A4 | HAZOP and SIL review & report | ENG
GS |  | x |  |  | 89 | 002 | 100 | 00 | A4 | HAZOP and SIL review & report - Gazeifier Section GS | GS
OS |  | x |  |  | 89 | 002 | 200 | 00 | A4 | HAZOP and SIL review & report - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 89 | 002 | 300 | 00 | A4 | HAZOP and SIL review & report - Boiler Section BS | BS
ES |  | x |  |  | 89 | 002 | 400 | 00 | A4 | HAZOP and SIL review & report - Electrical Generation Section ES | ES
TS |  | x |  |  | 89 | 002 | 500 | 00 | A4 | HAZOP and SIL review & report - Gaz Treatment Section TS | TS
Proce |  |  |  |  | 89 | 002 | 600 | 00 | A4 | HAZOP and SIL review & report - Utilities Section US | US
ALL | x | x |  |  | 89 | 003 | A | 00 | A4 | Action sheets HAZOP follow-up | ENG
GS |  | x |  |  | 89 | 003 | 100 | 00 | A4 | Action sheets HAZOP follow-up - Gazeifier Section GS | GS
OS |  | x |  |  | 89 | 003 | 200 | 00 | A4 | Action sheets HAZOP follow-up - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 89 | 003 | 300 | 00 | A4 | Action sheets HAZOP follow-up - Boiler Section BS | BS
ES |  | x |  |  | 89 | 003 | 400 | 00 | A4 | Action sheets HAZOP follow-up - Electrical Generation Section ES | ES
TS |  | x |  |  | 89 | 003 | 500 | 00 | A4 | Action sheets HAZOP follow-up - Gaz Treatment Section TS | TS
US |  |  |  |  | 89 | 003 | 600 | 00 | A4 | Action sheets HAZOP follow-up - Utilities Section US | US
ALL | x | x |  |  | 89 | 004 | A | 00 | A4 | SIL Report | ENG
GS |  | x |  |  | 89 | 004 | 100 | 00 | A4 | SIL Report - Gazeifier Section GS | GS
OS |  | x |  |  | 89 | 004 | 200 | 00 | A4 | SIL Report - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | hold | hold | 89 | 004 | 300 | 00 | A4 | SIL Report - Boiler Section BS | BS
ES |  | x |  |  | 89 | 004 | 400 | 00 | A4 | SIL Report - Electrical Generation Section ES | ES
TS |  | x |  |  | 89 | 004 | 500 | 00 | A4 | SIL Report - Gaz Treatment Section TS | TS
BE |  | x |  |  | 89 | 005 | A | 00 | A4 | Check of the achieved SIL level | ENG
GS |  | x |  |  | 89 | 005 | 100 | 00 | A4 | Check of the achieved SIL level - Gazeifier Section GS | GS
OS |  | x |  |  | 89 | 005 | 200 | 00 | A4 | Check of the achieved SIL level - Oxidizer and ashes Furnace Section OS | OS
BS |  | x |  |  | 89 | 005 | 300 | 00 | A4 | Check of the achieved SIL level - Boiler Section BS | BS
ES |  | x |  |  | 89 | 005 | 400 | 00 | A4 | Check of the achieved SIL level - Electrical Generation Section ES | ES
TS |  | x |  |  | 89 | 005 | 500 | 00 | A4 | Check of the achieved SIL level - Gaz Treatment Section TS | TS
HSE | x | x |  |  | 89 | 006 | A | 00 | A4 | HAZID Report | ENG
[5 empty] | 89 | 10 | A | 100 | A4 | Safety Analysis | GS
BE | x | x |  |  | 89 | 011 | 001 | 00 | A1 | ATEX area classification drawing - Layout | ENG
GS |  |  |  |  | 89 | 011 | 100 | 00 | A1 | ATEX area classification drawing - Layout - Gazeifier Section GS | GS
OS |  |  |  |  | 89 | 011 | 200 | 00 | A1 | ATEX area classification drawing - Layout - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 89 | 011 | 300 | 00 | A1 | ATEX area classification drawing - Layout - Boiler Section BS | BS
ES |  |  |  |  | 89 | 011 | 400 | 00 | A1 | ATEX area classification drawing - Layout - Electrical Generation Section ES | ES
TS |  |  |  |  | 89 | 011 | 500 | 00 | A1 | ATEX area classification drawing - Layout - Gaz Treatment Section TS | TS
HSE |  | x |  |  | 89 | 012 | A | 00 | A4 | Memorandum of classified areas / List of ATEX sources | ENG
BE | x | x |  |  | 89 | 021 | A | 00 | A4 | Noise equipment list | ENG
GS |  |  |  |  | 89 | 021 | 100 | 00 | A4 | Noise equipment list - Gazeifier Section GS | GS
OS |  |  |  |  | 89 | 021 | 200 | 00 | A4 | Noise equipment list - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | hold | hold | 89 | 021 | 300 | 00 | A4 | Noise equipment list - Boiler Section BS | BS
ES |  |  |  |  | 89 | 021 | 400 | 00 | A4 | Noise equipment list - Electrical Generation Section ES | ES
TS |  |  |  |  | 89 | 021 | 500 | 00 | A4 | Noise equipment list - Gaz Treatment Section TS | TS
BE |  |  |  |  | 89 | 021 | 600 | 00 | A4 | Noise equipment list - Utilities Section US | US
HSE | x | x |  |  | 89 | 022 | 001 | 00 | A1 | List of HSE items | ENG
GS |  |  |  |  | 89 | 022 | 100 | 00 | A1 | List of HSE items - Gazeifier Section GS | GS
OS |  |  |  |  | 89 | 022 | 200 | 00 | A1 | List of HSE items - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 89 | 022 | 300 | 00 | A1 | List of HSE items - Boiler Section BS | BS
ES |  |  |  |  | 89 | 022 | 400 | 00 | A1 | List of HSE items - Electrical Generation Section ES | ES
TS |  |  |  |  | 89 | 022 | 500 | 00 | A1 | List of HSE items - Gaz Treatment Section TS | TS
BE |  |  |  |  | 89 | 023 | 001 | 00 | A1 | Safety equipment layout | ENG
GS |  |  |  |  | 89 | 023 | 100 | 00 | A1 | Safety equipment layout - Gazeifier Section GS | GS
OS |  |  |  |  | 89 | 023 | 200 | 00 | A1 | Safety equipment layout - Oxidizer and ashes Furnace Section OS | OS
BS |  |  |  |  | 89 | 023 | 300 | 00 | A1 | Safety equipment layout - Boiler Section BS | BS
ES |  |  |  |  | 89 | 023 | 400 | 00 | A1 | Safety equipment layout - Electrical Generation Section ES | ES
TS |  |  |  |  | 89 | 023 | 500 | 00 | A1 | Safety equipment layout - Gaz Treatment Section TS | TS
BE |  | x |  |  | 89 | 031 | 500 | 00 | A4 | Etude de dispersion cheminée | ENG
BE |  | x |  |  | 89 | 033 | A | 00 | A4 | Risk analysis according to Directive 97/23/CE | ENG
|  |  |  | 90 | 3D model
|  |  |  | RFQ | 90 | 1 | A | 00 | A4 | 3D Model Review checking | ENG | [6 empty] | 2023-03-16
|  |  |  | RFQ | 90 | 2 | A | 00 | A4 | 3D Guide Procedure for Package Suppliers | ENG | [6 empty] | 2023-03-16
[5 empty] | 90 | 3 | A | 00 | A4 |  | ENG
BE |  | x |  |  | 90 | 4 | A | 00 | A1 | 3D model | ENG | [5 empty] | 030 | 2023-12-12 | 2023-12-12
GS |  | x |  |  | 90 | 4 | 100 | 00 | A1 | 3D model - Gazeifier Section GS | GS
OS |  | x |  |  | 90 | 4 | 200 | 00 | A1 | 3D model - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | G | hold | 90 | 4 | 300 | 00 | A1 | 3D model - Boiler Section BS | BS
ES |  | x |  |  | 90 | 4 | 400 | 00 | A1 | 3D model - Electrical Generation Section ES | ES
TS |  | x |  |  | 90 | 4 | 500 | 00 | A1 | 3D model - Gaz Treatment Section TS | TS
BE |  | x |  |  | 90 | 5 | A | 00 | A1 | 3D model - Reviews & report | ENG
GS |  | x |  |  | 90 | 5 | 100 | 00 | A1 | 3D model - Reviews & report - Gazeifier Section GS | GS
OS |  | x |  |  | 90 | 5 | 200 | 00 | A1 | 3D model - Reviews & report - Oxidizer and ashes Furnace Section OS | OS
WO615 |  | x | G | hold | 90 | 5 | 300 | 00 | A1 | 3D model - Reviews & report - Boiler Section BS | BS
ES |  | x |  |  | 90 | 5 | 400 | 00 | A1 | 3D model - Reviews & report - Electrical Generation Section ES | ES
TS |  | x |  |  | 90 | 5 | 500 | 00 | A1 | 3D model - Reviews & report - Gaz Treatment Section TS | TS
|  |  |  | 91 | PERMITTING | [5 empty] | ENG
PGO | x | x |  |  | 91 | 001 | A | 00 | A4 | Input for "Permis de Construire" | ENG
PGO |  |  |  |  | 91 | 002 | A | 00 | A4 | Input for "Permis D'exploiter" | ENG
PGO |  | ?? |  |  | 91 | 008 | A | 00 | A4 | Fire safety concept | ENG
|  |  |  | 92 | Precom & comm & test
|  | x |  |  | 92 | 1 | A | 00 | A4 | Liste des systèmes
|  | x |  |  | 92 | 2 | A | 00 | A4 | Procédures générales et fiches de réception instrumentation
|  | x |  |  | 92 | 3 | A | 00 | A4 | Plan de commissioning
WO615 |  |  | T | 920 | 92 | 3 | 300 | 00 | A4
COMMISSIONING PROCEDURE
|  | x |  |  | 92 | 4 | A | 00 | A4 | Plan de mise en route et d'essais
|  | x |  |  | 92 | 5 | A | 00 | A4 | Pre-com / com procedure & follow up
[5 empty] | 92 | 5 | 100 | 00 | A4 | Pre-com / com procedure & follow up - Gazeifier Section GS
[5 empty] | 92 | 5 | 200 | 00 | A4 | Pre-com / com procedure & follow up - Oxidizer and ashes Furnace Section OS
WO615 |  |  | P | 021 | 92 | 5 | 300 | 00 | A4 | Pre-com / com procedure & follow up - Boiler Section BS
[5 empty] | 92 | 5 | 400 | 00 | A4 | Pre-com / com procedure & follow up - Electrical Generation Section ES
[5 empty] | 92 | 5 | 500 | 00 | A4 | Pre-com / com procedure & follow up - Gaz Treatment Section TS
|  |  |  | 96 | CHEMICAL & CONSUMABLE | [5 empty] | ENG
BE | x | x |  |  | 96 | 1 | 001 | 00 | A4 | Chemical & consumer list & qtt & safety DS | ENG
GS |  |  |  |  | 96 | 1 | 100 | 00 | A4 | Chemical & consumer list & qtt & safety DS - Gazeifier Section GS | GS
OS |  |  |  |  | 96 | 1 | 200 | 00 | A4 | Chemical & consumer list & qtt & safety DS - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | hold | hold | 96 | 1 | 300 | 00 | A4 | Chemical & consumer list & qtt & safety DS - Boiler Section BS | BS
ES |  |  |  |  | 96 | 1 | 400 | 00 | A4 | Chemical & consumer list & qtt & safety DS - Electrical Generation Section ES | ES
TS |  |  |  |  | 96 | 1 | 500 | 00 | A4 | Chemical & consumer list & qtt & safety DS - Gaz Treatment Section TS | TS
|  |  |  | 97 | SPARE PARTS LIST | [5 empty] | ENG
DCC | x | x |  |  | 97 | 001 | A | 00 | A4 | Spare parts for commissining and startup | ENG
GS |  | x |  |  | 97 | 001 | 100 | 00 | A4 | Spare parts for commissining and startup - Gazeifier Section GS | GS
OS |  | x |  |  | 97 | 001 | 200 | 00 | A4 | Spare parts for commissining and startup - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | T | 110 | 97 | 001 | 300 | 00 | A4 | Spare parts for commissining and startup - Boiler Section BS | BS
ES |  | x |  |  | 97 | 001 | 400 | 00 | A4 | Spare parts for commissining and startup - Electrical Generation Section ES | ES
TS |  | x |  |  | 97 | 001 | 500 | 00 | A4 | Spare parts for commissining and startup - Gaz Treatment Section TS | TS
DCC | x | x |  |  | 97 | 002 | A | 00 | A4 | Spare parts list for 2 years operation | ENG
GS |  | x |  |  | 97 | 002 | 100 | 00 | A4 | Spare parts list for 2 years operation - Gazeifier Section GS | GS
OS |  | x |  |  | 97 | 002 | 200 | 00 | A4 | Spare parts list for 2 years operation - Oxidizer and ashes Furnace Section OS | OS
WO615 |  |  | T | 100 | 97 | 002 | 300 | 00 | A4 | Spare parts list for 2 years operation - Boiler Section BS | BS
ES |  | x |  |  | 97 | 002 | 400 | 00 | A4 | Spare parts list for 2 years operation - Electrical Generation Section ES | ES
TS |  | x |  |  | 97 | 002 | 500 | 00 | A4 | Spare parts list for 2 years operation - Gaz Treatment Section TS | TS
DCC |  | x |  |  | 97 | 002 | 600 | 00 | A4 | Spare parts list for 2 years operation - Utilities Section US | US
DCC | x | x |  |  | 97 | 3 | A | 00 | A4 | Special tools | ENG
GS |  | x |  |  | 97 | 3 | 100 | 00 | A4 | Special tools - Gazeifier Section GS | GS
Note on R60: Karine Lamoureux: +Native
Note on R61: Karine Lamoureux: +Native
Note on R62: Karine Lamoureux: +Native
Note on R63: Karine Lamoureux: +Native
Note on R64: Karine Lamoureux: +Native
Note on R65: Karine Lamoureux: +Native
Note on R66: Karine Lamoureux: +Native
Note on R67: Karine Lamoureux: +Native
Note on R68: Karine Lamoureux: +Native
Note on R69: Karine Lamoureux: +Native
Note on R72: Karine Lamoureux: +Native
Note on R73: Karine Lamoureux: +Native
Note on R74: Karine Lamoureux: +Native
Note on R75: Karine Lamoureux: +Native
Note on R76: Karine Lamoureux: +Native
Note on R77: Karine Lamoureux: +Native
Note on R79: Karine Lamoureux: +Native
Note on R80: Karine Lamoureux: +Native
Note on R82: Karine Lamoureux: +Native
Note on R83: Karine Lamoureux: +Native
Note on R84: Karine Lamoureux: +Native
Note on R85: Karine Lamoureux: +Native